## 4-11-2026
BLD Services, LLC - PRODUCTION & REVENUE REPORT
[6 empty] | Week Ending | 2026-04-11
Clean & CCTV | [5 empty] | Job Name: | Nashville - Hopedale Rehabilitation (Inliner) | [6 empty] | Job Number: |  | 26129
[6 empty] | Job Location: | Nashville TN | [6 empty] | Superintendent: |  | GIBBS |  |  |  | Inventory Usage
[17 empty] | VIDEO DETAILS |  |  | Tube |  |  |  |  | Resin |  | Collar
Sewer Type | Street Easement | LS / Area / Segment # / Repair # | UPS MH # | DWNS MH # | House Number | Street Name | Repair Location | Bid Item Number | Activity | Mainline Diameter | Lateral Diameter | Length | Quantity | Unit Price | Extended Total | Comments | Have Video ? | Reviewed ? | COMMENTS | Diameter | Mil | % cut | add'l info (if needed) | Tube (ft) | Resin Type | Resin (lbs) | Collar Type | Collar (ea)
|  |  | SUNDAY | 2026-04-05
|  |  | MONDAY | 2026-04-06
Sanitary Sewer | Street | A-064 | 147-08-049 | 147-04-079 |  |  |  | B-3 | Main Pre Video | 8" |  |  | 287.4 | 3.9 | 1120.86
Sanitary Sewer | Street | A-030 | 147-04-074 | 147-04-073 |  |  |  | B-3 | Main Pre Video | 8" |  |  | 112.2 | 3.9 | 437.58
Sanitary Sewer | Street | A-031 | 147-04-075 | 147-04-074 |  |  |  | B-3 | Main Pre Video | 8" |  |  | 193.5 | 3.9 | 754.65
Sanitary Sewer | Street | A-033 | 147-04-077 | 147-04-074 |  |  |  | B-3 | Main Pre Video | 8" |  |  | 123.2 | 3.9 | 480.48
Sanitary Sewer | Street | A-136 | 148-01-046 | 147-04-044 |  |  |  | B-3 | Main Pre Video | 8" |  |  | 374.3 | 3.9 | 1459.77
Sanitary Sewer | Street | A-137 | 148-01-047 | 148-01-046 |  |  |  | B-3 | Main Pre Video | 8" |  |  | 370.8 | 3.9 | 1446.12
Sanitary Sewer | Street | A-027 | 147-04-071 | 147-04-070 |  |  |  | B-3 | Main Pre Video | 8" |  |  | 73.1 | 3.9 | 285.09
Sanitary Sewer | Street | A-028 | 147-04-072 | 147-04-071 |  |  |  | B-3 | Main Pre Video | 8" |  |  | 101.5 | 3.9 | 395.85
|  |  | TUESDAY | 2026-04-07 | [10 empty] | 0
Sanitary Sewer | Street | [6 empty] | B-3 | Main Pre Video | 8" |  |  |  | 3.9 | 0
Sanitary Sewer | Street | [6 empty] | B-3 | Main Pre Video | 8" |  |  |  | 3.9 | 0
Sanitary Sewer | Street | [6 empty] | B-3 | Main Pre Video | 8" |  |  |  | 3.9 | 0
Sanitary Sewer | Street | [6 empty] | B-3 | Main Pre Video | 8" |  |  |  | 3.9 | 0
Sanitary Sewer | Street | [6 empty] | B-3 | Main Pre Video | 8" |  |  |  | 3.9 | 0
Sanitary Sewer | Street | [6 empty] | B-3 | Main Pre Video | 8" |  |  |  | 3.9 | 0
Sanitary Sewer | Street | [6 empty] | B-3 | Main Pre Video | 8" |  |  |  | 3.9 | 0
Sanitary Sewer | Street | [6 empty] | B-3 | Main Pre Video | 8" |  |  |  | 3.9 | 0
Sanitary Sewer | Street | [6 empty] | B-3 | Main Pre Video | 8" |  |  |  | 3.9 | 0
Sanitary Sewer | Street | [6 empty] | B-3 | Main Pre Video | 8" |  |  |  | 3.9 | 0
Sanitary Sewer | Street | [6 empty] | B-3 | Main Pre Video | 8" |  |  |  | 3.9 | 0
Sanitary Sewer | Street | [6 empty] | B-3 | Main Pre Video | 8" |  |  |  | 3.9 | 0
Sanitary Sewer | Street | [6 empty] | B-3 | Main Pre Video | 8" |  |  |  | 3.9 | 0
Sanitary Sewer | Street | [6 empty] | B-3 | Main Pre Video | 8" |  |  |  | 3.9 | 0
Sanitary Sewer | Street | [6 empty] | B-3 | Main Pre Video | 8" |  |  |  | 3.9 | 0
Sanitary Sewer | Street | [6 empty] | B-3 | Main Pre Video | 8" |  |  |  | 3.9 | 0
|  |  | WEDNESDAY | 2026-04-08 | [10 empty] | 0
|  |  | THURSDAY | 2026-04-09 | [10 empty] | 0
|  |  | FRIDAY | 2026-04-10 | [10 empty] | 0
Sanitary Sewer | Street | [6 empty] | B-55 | MH Sonde & Locate |  |  |  |  | 350 | 0
0
[7 empty] | MH Sonde & Locate | [7 empty] | 0
|  |  | SATURDAY | 2026-04-11 | [10 empty] | 0
0
[14 empty] | TOTAL | 6380.4 | [8 empty] | 0 |  | 0 |  | 0
Comments on Job Status:
[6 empty] | Tube diameter | Tube Milage | % cut | add'l info if needed | resin | resin | collar |  | reviewed videos
Additional Footage |  | 4" | Street | Sanitary Sewer |  | 3.75" | 3 mm | 92% | applied felt | Polyester 201 | Polyester 201 | 8" x 4" x 60deg |  | YES
Brush Taps |  | 5" | Easement | Storm Sewer |  | 4" | 4.5 mm | 95% | 2 layer | Vinyl Ester | Vinyl Ester | 8" x 4" x 90deg |  | NO
Bypass |  | 6" | Alley Way |  |  | 5" | 5 mm | 98% | 2 layer pull in |  |  | 8" x 6" x 60deg
Clean & Video |  | 7.5" |  |  |  | 5.5" | 6 mm |  | 2 layer inversion tube |  |  | 8" x 6" x 90deg
Clean Only |  | 8" |  |  |  | 5.875" | 7.5 mm |  | dense
Cleanout Shot |  | 10" |  |  |  | 6" | 9 mm
Coupon Removal |  | 12" |  |  |  | 7.375"
Cut Taps |  | 15" |  |  |  | 7.5"
Cut/Brush Taps |  | 16" |  |  |  | 7.75"
Drop Invert |  | 18" |  |  |  | 8"
Flagman |  | 21" |  |  |  | 9.5"
Install Cleanout in Grass |  | 24" |  |  |  | 10"
Internal Point Repair |  | 27" |  |  |  | 11.25"
Lateral Post Video |  | 30" |  |  |  | 11.5"
Lateral Pre Video | [5 empty] | 12"
Lateral Prep Video | [5 empty] | 14.25"
Lateral Launch | [5 empty] | 15"
Lower Cleanout on CIPPL Rehab | [5 empty] | 18"
Lower Existing Cleanout
Main Post Video
Main Pre Video
Mobilization
Obstruction Removal
Protruding Tap
Pull In
Root Removal
SCS+L - Brim Short Lateral
SCS+L - Brim Long Lateral
SCS+L - Full Wrap Short Lateral
SCS+L - Full Wrap Long Lateral
Service Line Point Repair in Grass
Set Up
Slug Removal
Spot Repair (Felt)
Spot Repair (Fiberglass)
Traffic set up
Video Only

## Mainline
Mainline Liner
Design Information | [10 empty] | Pre CCTV Information | [13 empty] | Liner Installation Information |  |  |  |  | Liner Testing Information |  |  |  | Post CCTV Information
CWN Item No. | SAC | SAC Revised | Existing Pipe Material | USMH | DSMH | Pipe Dia. | Street Name | Sheet No. | Plan Length | EAC Length | Pre CCTV Date | Camera Direction | Hard Tape Length | CCTV Length | Service Count | US MH Depth | US MH Diameter | DS MH Depth | DS MH Diameter | Mainline Material | Heavy Cleaning Length | Status | Bid Item Number | Pre-TV Notes | Date Installed | Installed Length | Contractor Shot No. | # of Services | Drop | Air Test? | Test PSI Start | Test PSI End | Air Test Pass/Fail | Post CCTV Date | Uploaded to MWS Date | Comments
A-001 | CCTV, JC | CCTV, JC | CIPP | 147-04-043 | 147-04-044 | 8 | WALLACE RD | 9/10 | 78 | 78 | 2026-04-03 | Downstream | 78 | 77.3 | 2 | 4' | 8" | 8.2' | 8" | CIPP | NA | Previously Lined | B-3 |  |  | 0 |  | 1
A-002 | CIPP | CIPP | VCP | 147-04-044 | 147-04-045 | 8 | FAULKNER DR | 9/10 | 158 | 160 | 2026-04-02 | Upstream | 160 | 159.8 | 0 | 8.2' | 8" | 6.5' | 8" | VCP | NA | Ready to Line | B-3 |  |  | 0 |  | 0
A-003 | CIPP | CIPP | VCP | 147-04-045 | 147-04-047 | 8 | FAULKNER DR | 9/10 | 38 | 38 | 2026-04-02 | Upstream | 38 | 37.1 | 0 | 6.5' | 8" | 6.7' | 8" | VCP | NA | Ready to Line | B-3 |  |  | 0 |  | 0
A-005 | CCTV | CCTV | CIPP | 147-04-047 | 147-04-048 | 8 | FAULKNER DR | 9/10 | 65 | 67 | 2026-04-03 | Downstream | 67 | 66.6 | 0 | 6.7' | 8" | 12' | 8" | CIPP | NA | Previously Lined | B-3 |  |  | 0 |  | 0
A-006 | CCTV, JC | CCTV, JC | CIPP | 147-04-048 | 147-04-049 | 8 | WALLACE RD | 9/10 | 127 | 127 | [15 empty] | 0 |  | 1
A-007 | CCTV, JC | CCTV, JC | CIPP | 147-04-049 | 147-04-093 | 8 | FAULKNER DR | 9/10 | 143 | 143 | [15 empty] | 0 |  | 1
A-009 | CCTV, JC | CCTV, JC | CIPP | 147-04-051 | 147-04-049 | 8 | FAULKNER DR | 9/10 | 84 | 84 | [15 empty] | 0 |  | 1
A-010 | CIPP | CIPP | VCP | 147-04-052 | 147-04-050 | 8 | FAULKNER DR | 9/10 | 167 | 167 | 2026-04-02 | Downstream | 167 | 166.7 | 2 | 5.5' | 8" | 7.2' | 8" | VCP | NA | Ready to Line | B-3 |  |  | 0 |  | 2
A-011 | CIPP | CIPP | VCP | 147-04-053 | 147-04-052 | 8 | WILLOW LN | 9/10 | 203 | 202 | 2026-04-02 | Upstream | 202 | 201.4 | 1 | 5.9' | 8" | 5.5' | 8" | VCP | NA | Needs Attention | B-3 | 72.8' TOTAL FEET OF PIPE HAS DEEP CRACKS AND BROKEN AREAS / FROM 93.3'-166.1' FROM DSMH 147-04-052 |  | 0 |  | 2
A-012 | CIPP | CIPP | VCP | 147-04-054 | 147-04-052 | 8 | FAULKNER DR | 9/10 | 123 | 122 | 2026-04-02 | Upstream | 122 | 121.9 | 0 | 6' | 8" | 5.5' | 8" | VCP | NA | Ready to Line | B-3 |  |  | 0 |  | 0
A-013 | CCTV; IR (3) | CCTV; IR (3) | CIPP | 147-04-055 | 147-04-051 | 8 | FAULKNER DR | 9/10 | 332 | 332 | [15 empty] | 0 |  | 4
A-014 | IR (1) | CCTV; IR (1) | CIPP | 147-04-056 | 147-04-055 | 8 | FAULKNER DR | 9/10 | 115 | 115 | [15 empty] | 0 |  | 2
A-015 | CIPP | CIPP | VCP | 147-04-057 | 147-04-054 | 8 | FAULKNER DR | 9/10 | 269 | 270 | 2026-04-02 | Upstream | 270 | 269.8 | 4 | BURIED | NA | 6' | 8" | VCP | NA | Needs Attention | B-3 | USMH 147-04-057 / BURIED - SONDE/LOCATED MARKED IN ROAD 7' DEEP |  | 0 |  | 4
A-016 | CIPP | CIPP | VCP | 147-04-058 | 147-08-014 | 8 | FAULKNER DR | 9/10/13/14 | 320 | 320 | [15 empty] | 0 |  | 5
A-024 | S-LTV | S-LTV | PVC | 147-04-068 | 147-04-085 | 8 | HUMBER DR | 9/10 | 125 | 125 | [15 empty] | 0 |  | 1
A-025 | CCTV, JC | CCTV, JC | PVC | 147-04-069 | 147-04-068 | 8 | HUMBER DR | 9/10 | 278 | 278 | [15 empty] | 0 |  | 3
A-026 | CCTV, JC | CCTV, JC | PVC | 147-04-070 | 147-04-069 | 8 | FOLEY DR | 9/10 | 255 | 255 | [15 empty] | 0 |  | 2
A-027 | CCTV | CCTV | DIP | 147-04-071 | 147-04-070 | 8 | FOLEY DR | 9/10 | 73 | 74 | 2026-04-06 | Downstream | 74 | 73.1 | 0 | 11' | 8" | 5.4' | 8" | Concrete | NA | Ready to Line | B-3 |  |  | 0 |  | 0
A-028 | CCTV | CCTV | PVC | 147-04-072 | 147-04-071 | 8 | FOLEY DR | 9/10 | 98 | 102 | 2026-04-06 | Upstream | 102 | 101.5 | 1 | 4.5' | 8" | 5.4' | 8" | PVC | NA | Ready to Line | B-3 |  |  | 0 |  | 2
A-029 | CCTV, JC | CCTV, JC | DIP | 147-04-073 | 147-04-081 | 8 | TORBAY DR | 9/10 | 258 | 258 | [15 empty] | 0 |  | 1
A-030 | CCTV, JC | CCTV, JC | PVC | 147-04-074 | 147-04-073 | 8 | TORBAY DR | 9/10 | 115 | 113 | 2026-04-06 | Downstream | 113 | 112.2 | 1 | 7.7' | 8" | 9.5' | 8" | PVC | NA | Ready to Line | B-3 |  |  | 0 |  | 1
A-031 | CCTV, JC | CCTV, JC | PVC | 147-04-075 | 147-04-074 | 8 | HUMBER DR | 9/10 | 193 | 194 | 2026-04-06 | Upstream | 194 | 193.5 | 0 | 12' | 8" | 7.7' | 8" | PVC | NA | Ready to Line | B-3 |  |  | 0 |  | 0
A-033 | CCTV, JC | CCTV, JC | PVC | 147-04-077 | 147-04-074 | 8 | TORBAY DR | 9/10 | 125 | 124 | 4/6/226 | Downstream | 124 | 123.2 | 2 | 7.8' | 8" | 7.7' | 8" | PVC | NA | Ready to Line | B-3 |  |  | 0 |  | 2
A-036 | CCTV, JC | CCTV, JC | PVC | 147-04-080 | 147-04-081 | 8 | WALLACE RD | 9/10 | 82 | 82 | [15 empty] | 0 |  | 1
A-037 | CCTV, JC | CCTV, JC | DIP | 147-04-081 | 147-04-082 | 8 | WALLACE RD | 9/10 | 177 | 177 | [15 empty] | 0 |  | 2
A-038 | CCTV | CCTV | PVC | 147-04-082 | RSSPSS25 | 8 | HUMBER DR | 9/10 | 26 | 26 | [15 empty] | 0 |  | 0
A-039 | CCTV | CCTV | PVC | 147-04-084 | 147-04-085 | 8 | WALLACE RD | 9/10 | 139 | 139 | [15 empty] | 0 |  | 0
A-041 | CCTV, JC | CCTV, JC | PVC | 147-04-092 | 147-04-082 | 8 | HUMBER DR | 9/10 | 83 | 83 | [15 empty] | 0 |  | 0
A-045 | CCTV | CCTV | PVC | 147-04-105 | 147-04-084 | 8 | WALLACE COURT | 9/10 | 45 | 45 | [15 empty] | 0 |  | 0
A-047 | S-PR, IR (2) | CCTV; S-PR, IR (2) | CIPP | 147-08-011 | 147-08-010 | 8 | FAULKNER DR | 13/14 | 381 | 381 | [15 empty] | 0 |  | 5
A-049 | CIPP; S-PR(2), IR (4) | CIPP | VCP | 147-08-013 | 147-08-098 | 8 | FAULKNER DR | 13/14 | 94 | 94 | [15 empty] | 0 |  | 2
A-050 | CIPP | CIPP | VCP | 147-08-014 | 147-08-015 | 8 | FAULKNER DR | 13/14 | 293 | 293 | [15 empty] | 0 |  | 4
A-053 | S-LTV (1) | S-LTV (1) | CIPP | 147-08-017 | 147-08-016 | 8 | FAULKNER DR | 13/14 | 283 | 283 | [15 empty] | 0 |  | 2
A-054 | CIPP, S-PR (4), IR (8) | CIPP | VCP | 147-08-018 | 147-08-019 | 8 | FAULKNER DR | 13/14 | 226 | 226 | [15 empty] | 0 |  | 4
A-055 | CIPP, S-PR (2), IR (4) | CIPP | VCP | 147-08-019 | 147-08-020 | 8 | FAULKNER DR | 13/14 | 241 | 241 | [15 empty] | 0 |  | 2
A-056 | CIPP, S-PR (2), IR (4) | CIPP | VCP | 147-08-020 | 147-08-021 | 8 | FAULKNER DR | 13/14 | 119 | 119 | [15 empty] | 0 |  | 4
A-059 | CCTV | CCTV | PVC | 147-08-039 | 147-08-067 | 8 | TORBAY DR | 13/14 | 31 | 31 | [15 empty] | 0 |  | 0
A-060 | CCTV, JC | CCTV, JC | DIP | 147-08-040 | 147-08-039 | 8 | WALES DR | 13/14 | 100 | 100 | [15 empty] | 0 |  | 0
A-062 | CCTV | CCTV | PVC | 147-08-047 | 147-08-046 | 8 | HUMBER DR | 13/14 | 299 | 299 | [15 empty] | 0 |  | 3
A-063 | CCTV, JC | CCTV, JC | PVC | 147-08-048 | 147-08-047 | 8 | HUMBER DR | 13/14 | 69 | 69 | [15 empty] | 0 |  | 2
A-064 | S-LL (1) | S-LL (1) | PVC | 147-08-049 | 147-04-079 | 8 | TORBAY DR | 9/10/13/14 | 269 | 288 | 2026-04-06 | Downstream | 288 | 287.4 | 3 | 8.5' | 8" | 7.9' | 8" | PVC | NA | Ready to Line | B-3 |  |  | 0 |  | 3
A-069 | S-LTV (2) | S-LTV (2) | PVC | 147-08-054 | 147-08-053 | 8 | WALES CT | 13/14 | 269 | 269 | [15 empty] | 0 |  | 4
A-070 | CCTV, JC | CCTV, JC | PVC | 147-08-055 | 147-08-054 | 8 | WALES CT | 13/14 | 157 | 157 | [15 empty] | 0 |  | 3
A-071 | S-LTV(1) | S-LTV(1) | PVC | 147-08-056 | 147-08-055 | 8 | WALES CT | 13/14 | 125 | 125 | [15 empty] | 0 |  | 2
A-072 | CCTV, S-PR (1), IR (2) | CCTV, S-PR (1), IR (2) | PVC | 147-08-057 | 147-08-056 | 8 | WALES CT | 13/14 | 91 | 91 | [15 empty] | 0 |  | 2
A-075 | CCTV, JC, EX (1), S-PR (1), IR (2) | CCTV, JC, EX (1), S-PR (1), IR (2) | PVC | 147-08-060 | 147-08-059 | 8 | WALES CT | 13/14 | 183 | 183 | [15 empty] | 0 |  | 3
A-076 | CCTV; JC; EX (2) | CCTV; JC; EX (2) | PVC | 147-08-061 | 147-08-060 | 8 | WALES CT | 13/14 | 255 | 255 | [15 empty] | 0 |  | 2
A-077 | CCTV, JC | CCTV, JC | PVC | 147-08-062 | 147-08-061 | 8 | WALES CT | 13/14 | 292 | 292 | [15 empty] | 0 |  | 3
A-078 | S-LTV (1) | S-LTV (1) | PVC | 147-08-063 | 147-08-062 | 8 | WALES DR | 13/14 | 80 | 80 | [15 empty] | 0 |  | 3
A-083 | IR | CCTV; IR | PVC | 147-08-068 | 147-08-067 | 8 | WALES DR | 22/23 | 227 | 227 | [15 empty] | 0 |  | 1
A-086 | CCTV, JC | CCTV, JC | PVC | 147-08-071 | 147-08-070 | 8 | WALES DR | 13/14 | 145 | 145 | [15 empty] | 0 |  | 2
A-088 | S-PR (2), IR (4) | CCTV; S-PR (2), IR (4) | PVC | 147-08-073 | 147-08-071 | 8 | HOPEDALE DR | 13/14 | 270 | 270 | [15 empty] | 0 |  | 3
A-093 | CCTV, JC, S-PR(2), IR (4) | CCTV, JC, S-PR(2), IR (4) | PVC | 147-08-078 | 147-08-077 | 8 | HUMBER DR | 13/14 | 128 | 128 | [15 empty] | 0 |  | 2
A-097 | CCTV | CCTV | DIP | 147-08-082 | 147-08-074 | 8 | HOPEDALE DR | 13/14 | 215 | 215 | [15 empty] | 0 |  | 0
A-098 | CCTV, JC | CCTV, JC | PVC | 147-08-096 | 147-08-100 | 8 | HOLLIS HILL DR | 13/14 | 173 | 173 | [15 empty] | 0 |  | 1
A-100 | CIPP, S-PR(4), IR (8) | CIPP | VCP | 147-08-098 | 147-08-012 | 8 | FAULKNER DR | 13/14 | 325 | 325 | [15 empty] | 0 |  | 4
A-102 | CCTV | CCTV | PVC | 147-08-100 | 147-08-098 | 8 | HOLLIS HILL DR | 13/14 | 124 | 124 | [15 empty] | 0 |  | 0
A-103 | CCTV, JC | CCTV, JC | DIP | 147-08-101 | 147-08-102 | 8 | HOLLIS HILL DR | 13/14 | 212 | 212 | [15 empty] | 0 |  | 3
A-104 | CCTV | CCTV | PVC | 147-08-102 | 147-08-096 | 8 | HOLLIS HILL DR | 13/14 | 204 | 204 | [15 empty] | 0 |  | 3
A-106 | CIPP | CIPP | UNK | 148-09-029 | 148-09-030 | 8 | FAULKNER DR | 19/20 | 108 | 108 | [15 empty] | 0 |  | 4
A-108 | CCTV | CCTV | PVC | 147-12-043 | 147-12-064 | 8 | CARAWAY DR | 17/18 | 138 | 138 | [15 empty] | 0
A-110 | CCTV | CCTV | PVC | 147-12-045 | 147-12-063 | 8 | CARAWAY DR | 17/18 | 142 | 142 | [15 empty] | 0
A-111 | CCTV | CCTV | DIP | 147-12-046 | 147-08-040 | 8 | CARAWAY DR | 13/14/17/18 | 153 | 153 | [15 empty] | 0 |  | 0
A-123 | CCTV | CCTV | PVC | 147-12-063 | 147-12-046 | 8 | CARAWAY DR | 17/18 | 159 | 159 | [15 empty] | 0 |  | 1
A-124 | CCTV | CCTV | PVC | 147-12-064 | 147-12-044 | 8 | CARAWAY DR | 17/18 | 139 | 139 | [15 empty] | 0
A-126 | CIPP, S-PR (3), IR (6) | CIPP | VCP | 148-01-036 | 147-08-018 | 8 | TURLEY DR | 9/10/11/12/13/14 | 229 | 229 | [15 empty] | 0 |  | 3
A-127 | CIPP, EX, S-PR (1), IR (2) | CIPP | VCP | 148-01-037 | 148-01-036 | 8 | TURLEY DR | 11/12 | 114 | 114 | [15 empty] | 0 |  | 1
A-128 | JC, CIPP, S-PR(1), IR (2) | CIPP | VCP | 148-01-038 | 148-01-037 | 8 | TURLEY DR | 11/12 | 91 | 91 | [15 empty] | 0 |  | 1
A-129 | CIPP | CIPP | VCP | 148-01-039 | 147-04-053 | 8 | WILLOW LN | 9/10/11/12 | 196 | 199 | 2026-04-02 | Upstream | 199 | 198.9 | 4 | 5.6' | 8" | 5.9' | 8" | VCP | NA | Needs Attention | B-3 | MATERIAL SETTLED/BONDED TO PIPE 1-2' FROM USMH 148-01-039 / INFILTRATION 124.6' FROM DSMH 147-04-053 |  | 0 |  | 4
A-130 | CIPP | CIPP | VCP | 148-01-040 | 148-01-039 | 8 | WILLOW LN | 11/12 | 132 | 133 | 2026-04-02 | Upstream | 133 | 132.7 | 2 | 5.4' | 8" | 5.6' | 8" | VCP | NA | Ready to Line | B-3 |  |  | 0 |  | 2
A-131 | CIPP, S-PR(5), IR (10) | CIPP | VCP | 148-01-041 | 147-04-046 | 8 | WALLACE RD | 9/10/11/12 | 189 | 189 | [15 empty] | 0 |  | 5
A-132 | CCTV, S-PR (2), IR (4), S-LTV (3) | CCTV, S-PR (2), IR (4), S-LTV (3) | CIPP | 148-01-042 | 148-01-041 | 8 | WALLACE RD | 11/12 | 282 | 282 | [15 empty] | 0 |  | 3
A-133 | CIPP; S-PR(2), IR (4) | CIPP | VCP | 148-01-043 | 148-01-042 | 8 | TURLEY DR | 11/12 | 103 | 103 | [15 empty] | 0 |  | 2
A-134 | CIPP, S-PR (2), IR (4) | CIPP | VCP | 148-01-044 | 148-01-043 | 8 | TURLEY DR | 11/12 | 165 | 165 | [15 empty] | 0 |  | 2
A-135 | CIPP | CIPP | VCP | 148-01-045 | 148-01-044 | 8 | TURLEY DR | 11/12 | 227 | 227 | [15 empty] | 0 |  | 4
A-136 | CCTV, JC, S-PR(2), IR (4) | CCTV, JC, S-PR(2), IR (4) | CIPP | 148-01-046 | 147-04-044 | 8 | WALLACE RD | 9/10/11/12 | 373 | 375 | 2026-04-06 | Downstream | 375 | 374.3 | 5 | 10.5' | 8" | 8.2' | 8" | PVC | NA | PVC | B-3 |  |  | 0 |  | 2
A-137 | CCTV, JC | CCTV, JC | CIPP | 148-01-047 | 148-01-046 | 8 | WALLACE RD | 11/12 | 379 | 371 | 2026-04-06 | Upstream | 371 | 370.8 | 4 | 6' | 8" | 10.5' | 8" | CIPP | NA | Previously Lined | B-3 |  |  | 0 |  | 4
A-138 | CIPP, JC, S-PR(3), IR (6) | CIPP | VCP | 148-01-048 | 148-01-047 | 8 | WALLACE RD | 11/12 | 168 | 169 | 2026-04-03 | Downstream | 169 | 168.1 | 1 | 9.9' | 8" | 6' | 8" | CIPP | NA | Previously Lined | B-3 |  |  | 0 |  | 4
A-139 | CCTV, JC | CCTV, JC | CIPP | 148-01-072 | 148-01-048 | 8 | WALLACE RD | 11/12 | 67 | 72 | 2026-04-03 | Upstream | 72 | 71.1 | 2 | 4.5' | 8" | 9.9' | 8" | CIPP | NA | Previously Lined | B-3 |  |  | 0 |  | 2
A-140 | CCTV, JC, S-PR (1), IR (2) | CCTV, JC, S-PR (1), IR (2) | CIPP | 148-01-090 | 148-01-041 | 8 | WILLOW LN | 11/12 | 275 | 275 | [15 empty] | 0 |  | 3
A-141 | CCTV, IR(2) | CCTV, IR(2) | CIPP | 148-05-001 | 147-08-017 | 8 | LEOPOLE RD | 13/14/15/16 | 282 | 282 | [15 empty] | 0 |  | 2
A-142 | IR (3) | IR (3) | CIPP | 148-05-002 | 148-05-001 | 8 | LEOPOLE RD | 15/16 | 208 | 208 | [15 empty] | 0 |  | 3
A-143 | S-PR(1); IR(2); S-LTV (1) for service being relocated to MH; New MH as noted | CCTV; S-PR(1); IR(2); S-LTV (1) for service being relocated to MH; New MH as noted | CIPP | 148-05-003 | 148-05-002 | 8 | LEOPOLE RD | 15/16 | 312 | 312 | [15 empty] | 0 |  | 4
A-144 | CCTV | CCTV | CIPP | 148-05-004 | 147-08-017 | 8 | FAULKNER DR | 13/14/15/16 | 138 | 138 | [15 empty] | 0 |  | 1
A-147 | S-PR(1), IR (2) | CCTV; S-PR(1), IR (2) | CIPP | 148-05-007 | 148-05-004 | 8 | LEOPOLE RD | 15/16 | 169 | 169 | [15 empty] | 0 |  | 2
A-149 | EX(3); S-PR(3); IR(6) | CCTV; EX(3); S-PR(3); IR(6) | CIPP | 148-05-009 | 148-05-008 | 8 | LEOPOLE RD | 15/16 | 198 | 198 | [15 empty] | 0 |  | 3
A-150 | S-PR(1), IR (2) | CCTV; S-PR(1), IR (2) | CIPP | 148-05-010 | 148-05-009 | 8 | TURLEY DR | 15/16 | 89 | 89 | [15 empty] | 0 |  | 1
A-152 | CIPP, S-PR(7), IR (12) | CIPP | VCP | 148-05-012 | 148-05-011 | 8 | TURLEY DR | 15/16 | 332 | 332 | [15 empty] | 0 |  | 6
A-153 | CIPP; S-PR(1), IR (2) | CIPP | VCP | 148-05-013 | 147-08-018 | 8 | TURLEY DR | 13/14/15/16 | 61 | 61 | [15 empty] | 0 |  | 1
A-154 | CCTV | CCTV | PVC | 148-05-097 | 148-05-008 | 8 | TURLEY DR | 15/16 | 80 | 80 | [15 empty] | 0 |  | 1
A-157 | CCTV | CCTV | PVC | 147-04-104 | 147-04-105 | 8 | WALLACE Road | 9/10 | 173 | 173 | [15 empty] | 0 |  | 0
A-201 | CIPP; S-LL (1) | CIPP; S-LL (1) | CIP/CONC | 107-05-010 | 107-05-009 | 8 | ELISSA DR/DABBS AVE | 25/26 | 106 | 106 | [15 empty] | 0 |  | 1
A-202 | S-LL (5) | S-LL (5) | CIPP | 107-05-011 | 107-05-009 | 18 | ELISSA DR | 25/26 | 358 | 358 | [15 empty] | 0 |  | 5
A-203 | CIPP; S-LL(2) | CIPP; S-LL(2) | CONC | 107-05-012 | 107-05-010 | 8 | ELISSA DR | 25/26 | 361 | 361 | [15 empty] | 0 |  | 7
A-204 | S-LL (2) | S-LL (2) | CIPP | 107-05-013 | 107-05-011 | 18 | ELISSA DR | 25/26 | 143 | 143 | [15 empty] | 0 |  | 2
A-205 | S-LL(3) | S-LL(3) | CIPP | 107-05-014 | 107-05-013 | 15 | ELISSA DR | 25/26 | 285 | 285 | [15 empty] | 0 |  | 3
A-206 | CIPP; S-LL(7); IR(1) | CIPP; S-LL(7); IR(1) | CONC/CIP | 107-05-015 | 107-05-012 | 8 | PATRICIA DR | 25/26 | 339 | 339 | [15 empty] | 0 |  | 7
A-207 | CIPP; S-LL(2); EX | CIPP; S-LL(2); EX | CONC | 107-05-020 | 107-05-015 | 8 | PATRICIA DR | 25/26 | 245 | 245 | [15 empty] | 0 |  | 2
A-208 | CIPP; EX | CIPP; EX | CONC | 107-05-021 | 107-05-020 | 8 | KAREN DR | 25/26 | 110 | 110 | [15 empty] | 0 |  | 0
A-209 | CIPP; IR; S-LL (4) | CIPP; IR; S-LL (4) | CONC | 107-05-022 | 107-05-021 | 8 | KAREN DR | 25/26 | 182 | 182 | [15 empty] | 0 |  | 4
A-210 | CIPP; IR; S-LL(5) | CIPP; IR; S-LL(5) | CONC | 107-05-024 | 107-05-020 | 8 | PATRICIA DR | 25/26 | 393 | 393 | [15 empty] | 0 |  | 5
A-211 | CIPP; S-LL(3) | CIPP; S-LL(3) | CONC | 107-05-025 | 107-05-021 | 8 | PATRICIA DR | 25/26 | 325 | 325 | [15 empty] | 0 |  | 3
A-212 | CIPP; S-LL(2) | CIPP; S-LL(2) | VCP | 107-05-052 | 107-05-053 | 8 | PATRICIA DR | 25/26 | 152 | 152 | [15 empty] | 0 |  | 2
A-213 | CCTV; IR(2) | CCTV; IR(2) | CIPP | 107-05-054 | 107-05-014 | 8 | ELISSA DR | 25/26 | 113 | 113 | [15 empty] | 0 |  | 0
A-214 | CIPP; S-LL(4) | CIPP; S-LL(4) | CONC | 107-05-077 | 107-05-024 | 8 | PATRICIA DR | 25/26 | 268 | 268 | [15 empty] | 0 |  | 4
A-215 | CIPP; IR | CIPP; IR | VCP | 107-05-081 | 107-05-022 | 8 | KAREN DR | 25/26 | 201 | 201 | [15 empty] | 0 |  | 0
A-216 | CIPP; EX (2); S-LL(3) | CIPP; EX (2); S-LL(3) | VCP | 107-05-082 | 107-05-081 | 8 | KAREN DR | 25/26 | 164 | 164 | [15 empty] | 0 |  | 4
A-217 | CIPP; S-LL(4); | CIPP; S-LL(4); | CONC | 107-05-087 | 107-05-077 | 8 | PATRICIA DR | 25/26 | 191 | 191 | [15 empty] | 0 |  | 4
A-218 | CIPP; IR; S-LL(4) | CIPP; IR; S-LL(4) | VCP | 107-09-039 | 107-005-083 | 8 | FIVE OAKS DR | 25/26/27/28 | 239 | 239 | [15 empty] | 0 |  | 4
A-219 | CIPP; IR(1) | CIPP; IR(1) | VCP | 107-09-041 | 107-09-040 | 8 | MASSMAN DR | 27/28 | 61 | 61 | [15 empty] | 0 |  | 0
A-220 | S-LL(1) | S-LL(1) | DIP | 107-09-042 | 107-09-041 | 8 | MASSMAN DR | 27/28 | 141 | 141 | [15 empty] | 0 |  | 1
A-221 | CIPP; S-LL (1) | CIPP; S-LL (1) | VCP | 107-09-043 | 107-09-042 | 8 | MASSMAN DR | 27/28 | 136 | 136 | [15 empty] | 0 |  | 1
A-222 | S-LL(1) | S-LL(1) | DIP | 107-09-044 | 107-09-043 | 8 | MASSMAN DR | 27/28 | 128 | 128 | [15 empty] | 0 |  | 1
A-223 | CIPP; S-LL(2) | CIPP; S-LL(2) | VCP | 107-09-045 | 107-09-044 | 8 | MASSMAN DR | 27/28 | 166 | 166 | [15 empty] | 0 |  | 2
A-224 | CIPP; S-LL(1) | CIPP; S-LL(1) | VCP | 107-09-046 | 107-09-045 | 8 | MASSMAN DR | 27/28 | 75 | 75 | [15 empty] | 0 |  | 1
A-225 | CIPP; S-LL(1) | CIPP; S-LL(1) | VCP | 107-09-049 | 107-09-048 | 8 | MASSMAN DR | 27/28 | 57 | 57 | [15 empty] | 0 |  | 1
A-226 | CIPP | CIPP | CONC/CIP | 107-10-015 | 107-10-002 | 12 | GLASTONBURY BLVD | 29/30 | 60 | 60 | [15 empty] | 0 |  | 0
[10 empty] | 0 | [15 empty] | 0
[10 empty] | 0 | [15 empty] | 0
[10 empty] | 0 | [15 empty] | 0
[10 empty] | 0 | [15 empty] | 0
[10 empty] | 0 | [15 empty] | 0
[10 empty] | 0 | [15 empty] | 0
[10 empty] | 0 | [15 empty] | 0
[10 empty] | 0 | [15 empty] | 0
[10 empty] | 0 | [15 empty] | 0
[10 empty] | 0 | [15 empty] | 0

## 4-4-2026
BLD Services, LLC - PRODUCTION & REVENUE REPORT
[6 empty] | Week Ending | 2026-04-04
Clean & CCTV | [5 empty] | Job Name: | Nashville - Hopedale Rehabilitation (Inliner) | [6 empty] | Job Number: |  | 26129
[6 empty] | Job Location: | Nashville TN | [6 empty] | Superintendent: |  | GIBBS |  |  |  | Inventory Usage
[17 empty] | VIDEO DETAILS |  |  | Tube |  |  |  |  | Resin |  | Collar
Sewer Type | Street Easement | LS / Area / Segment # / Repair # | UPS MH # | DWNS MH # | House Number | Street Name | Repair Location | Bid Item Number | Activity | Mainline Diameter | Lateral Diameter | Length | Quantity | Unit Price | Extended Total | Comments | Have Video ? | Reviewed ? | COMMENTS | Diameter | Mil | % cut | add'l info (if needed) | Tube (ft) | Resin Type | Resin (lbs) | Collar Type | Collar (ea)
|  |  | SUNDAY | 2026-03-29 | [10 empty] | 0
|  |  | MONDAY | 2026-03-30 | [10 empty] | 0
|  |  | TUESDAY | 2026-03-31 | [10 empty] | 0
|  |  | WEDNESDAY | 2026-04-01 | [10 empty] | 0
|  |  | THURSDAY | 2026-04-02 | [10 empty] | 0
Sanitary Sewer | Street | A-012 | 147-04-054 | 147-04-052 |  | Faulkner Dr |  | B-3 | Main Pre Video | 8" |  |  | 121.9 | 3.9 | 475.41
Sanitary Sewer | Street | A-015 | 147-04-057 | 147-04-054 |  | Faulkner Dr |  | B-3 | Main Pre Video | 8" |  |  | 269.8 | 3.9 | 1052.22
Sanitary Sewer | Street |  | 147-04-057 |  |  |  |  | B-55 | MH Sonde & Locate |  |  |  | 1 | 350 | 350 | USMH 147-04-057 / BURIED - SONDE/LOCATED MARKED IN ROAD 7' DEEP
Sanitary Sewer | Street | A-010 | 147-04-052 | 147-04-050 |  | Faulkner Dr |  | B-3 | Main Pre Video | 8" |  |  | 166.7 | 3.9 | 650.13
Sanitary Sewer | Street | A-011 | 147-04-053 | 147-04-052 |  | Faulkner Dr |  | B-3 | Main Pre Video | 8" |  |  | 201.4 | 3.9 | 785.46
Sanitary Sewer | Street | A-129 | 148-01-039 | 147-04-053 |  | Willow Ln |  | B-3 | Main Pre Video | 8" |  |  | 198.9 | 3.9 | 775.71
Sanitary Sewer | Street | A-130 | 148-01-040 | 148-01-039 |  | Willow Ln |  | B-3 | Main Pre Video | 8" |  |  | 132.7 | 3.9 | 517.53
Sanitary Sewer | Street | A-002 | 147-04-044 | 147-04-045 |  | Faulkner Dr |  | B-3 | Main Pre Video | 8" |  |  | 159.8 | 3.9 | 623.22
Sanitary Sewer | Street | A-003 | 147-04-045 | 147-04-047 |  | Faulkner Dr |  | B-3 | Main Pre Video | 8" |  |  | 37.1 | 3.9 | 144.69
|  |  | FRIDAY | 2026-04-03 | [10 empty] | 0
Sanitary Sewer | Street | A-005 | 147-04-047 | 147-04-048 |  | Faulkner Dr |  | B-3 | Main Pre Video | 8" |  |  | 66.6 | 3.9 | 259.74
Sanitary Sewer | Street | A-138 | 148-01-048 | 148-01-047 |  | Wallace rd |  | B-3 | Main Pre Video | 8" |  |  | 168.1 | 3.9 | 655.59
Sanitary Sewer | Street | A-139 | 148-01-072 | 148-01-048 |  | Wallace rd |  | B-3 | Main Pre Video | 8" |  |  | 71.1 | 3.9 | 277.29
Sanitary Sewer | Street | A-001 | 147-04-043 | 147-04-044 |  | Wallace rd |  | B-3 | Main Pre Video | 8" |  |  | 77.3 | 3.9 | 301.47
0
[7 empty] | MH Sonde & Locate | [7 empty] | 0
|  |  | SATURDAY | 2026-04-04 | [10 empty] | 0
0
[14 empty] | TOTAL | 6868.46 | [8 empty] | 0 |  | 0 |  | 0
Comments on Job Status:
[6 empty] | Tube diameter | Tube Milage | % cut | add'l info if needed | resin | resin | collar |  | reviewed videos
Additional Footage |  | 4" | Street | Sanitary Sewer |  | 3.75" | 3 mm | 92% | applied felt | Polyester 201 | Polyester 201 | 8" x 4" x 60deg |  | YES
Brush Taps |  | 5" | Easement | Storm Sewer |  | 4" | 4.5 mm | 95% | 2 layer | Vinyl Ester | Vinyl Ester | 8" x 4" x 90deg |  | NO
Bypass |  | 6" | Alley Way |  |  | 5" | 5 mm | 98% | 2 layer pull in |  |  | 8" x 6" x 60deg
Clean & Video |  | 7.5" |  |  |  | 5.5" | 6 mm |  | 2 layer inversion tube |  |  | 8" x 6" x 90deg
Clean Only |  | 8" |  |  |  | 5.875" | 7.5 mm |  | dense
Cleanout Shot |  | 10" |  |  |  | 6" | 9 mm
Coupon Removal |  | 12" |  |  |  | 7.375"
Cut Taps |  | 15" |  |  |  | 7.5"
Cut/Brush Taps |  | 16" |  |  |  | 7.75"
Drop Invert |  | 18" |  |  |  | 8"
Flagman |  | 21" |  |  |  | 9.5"
Install Cleanout in Grass |  | 24" |  |  |  | 10"
Internal Point Repair |  | 27" |  |  |  | 11.25"
Lateral Post Video |  | 30" |  |  |  | 11.5"
Lateral Pre Video | [5 empty] | 12"
Lateral Prep Video | [5 empty] | 14.25"
Lateral Launch | [5 empty] | 15"
Lower Cleanout on CIPPL Rehab | [5 empty] | 18"
Lower Existing Cleanout
Main Post Video
Main Pre Video
Mobilization
Obstruction Removal
Protruding Tap
Pull In
Root Removal
SCS+L - Brim Short Lateral
SCS+L - Brim Long Lateral
SCS+L - Full Wrap Short Lateral
SCS+L - Full Wrap Long Lateral
Service Line Point Repair in Grass
Set Up
Slug Removal
Spot Repair (Felt)
Spot Repair (Fiberglass)
Traffic set up
Video Only

## Services
Service Connections
Design Information | [10 empty] | CWN Office Use Only |  | Excavation Services | [8 empty] | CIPP Services |  |  | Service Testing
CWN Item No. | Pipe Dia. | USHM | DSMH | Distance from USMH | Clock Position | House # | Street Name Prefix | Street Name | Street Name Suffix | Launch Date | CWN Recommendations (Subject to Change) | Launch Notes | Cleanout Install Date | C/O Size | C/O Depth (FT) | Length Installed | Extra Pipe | Tie In Material | Traffic Box | Inside Roadway? | Hard Surface Repair Needed | CIPP Liner Install Date | Length Installed | Extra Length | Date Tested | PSI Start | PSI End | Pass/Fail | Failure Method | Date Posted | Comments
A-001 | 8 | 147-04-043 | 147-04-044 |  |  |  |  | WALLACE | Road | [7 empty] | 0 | [6 empty] | 0
A-002 | 8 | 147-04-044 | 147-04-045 |  |  |  |  | FAULKNER | Drive | [7 empty] | 0 | [6 empty] | 0
A-003 | 8 | 147-04-045 | 147-04-047 |  |  |  |  | FAULKNER | Drive | [7 empty] | 0 | [6 empty] | 0
A-005 | 8 | 147-04-047 | 147-04-048 |  |  |  |  | FAULKNER | Drive | [7 empty] | 0 | [6 empty] | 0
A-006 | 8 | 147-04-048 | 147-04-049 |  |  |  |  | WALLACE | Road | [7 empty] | 0 | [6 empty] | 0
A-007 | 8 | 147-04-049 | 147-04-093 |  |  |  |  | FAULKNER | Drive | [7 empty] | 0 | [6 empty] | 0
A-009 | 8 | 147-04-051 | 147-04-049 |  |  |  |  | FAULKNER | Drive | [7 empty] | 0 | [6 empty] | 0
A-010 | 8 | 147-04-052 | 147-04-050 |  |  |  |  | FAULKNER | Drive | [7 empty] | 0 | [6 empty] | 0
A-011 | 8 | 147-04-053 | 147-04-052 |  |  |  |  | WILLOW | Lane | [7 empty] | 0 | [6 empty] | 0
A-012 | 8 | 147-04-054 | 147-04-052 |  |  |  |  | FAULKNER | Drive | [7 empty] | 0 | [6 empty] | 0
A-013 | 8 | 147-04-055 | 147-04-051 |  |  |  |  | FAULKNER | Drive | [7 empty] | 0 | [6 empty] | 0
A-014 | 8 | 147-04-056 | 147-04-055 |  |  |  |  | FAULKNER | Drive | [7 empty] | 0 | [6 empty] | 0
A-015 | 8 | 147-04-057 | 147-04-054 |  |  |  |  | FAULKNER | Drive | [7 empty] | 0 | [6 empty] | 0
A-016 | 8 | 147-04-058 | 147-08-014 |  |  |  |  | FAULKNER | Drive | [7 empty] | 0 | [6 empty] | 0
A-024 | 8 | 147-04-068 | 147-04-085 |  |  |  |  | HUMBER | Drive | [7 empty] | 0 | [6 empty] | 0
A-025 | 8 | 147-04-069 | 147-04-068 |  |  |  |  | HUMBER | Drive | [7 empty] | 0 | [6 empty] | 0
A-026 | 8 | 147-04-070 | 147-04-069 |  |  |  |  | FOLEY | Drive | [7 empty] | 0 | [6 empty] | 0
A-027 | 8 | 147-04-071 | 147-04-070 |  |  |  |  | FOLEY | Drive | [7 empty] | 0 | [6 empty] | 0
A-028 | 8 | 147-04-072 | 147-04-071 |  |  |  |  | FOLEY | Drive | [7 empty] | 0 | [6 empty] | 0
A-029 | 8 | 147-04-073 | 147-04-081 |  |  |  |  | TORBAY | Drive | [7 empty] | 0 | [6 empty] | 0
A-030 | 8 | 147-04-074 | 147-04-073 |  |  |  |  | TORBAY | Drive | [7 empty] | 0 | [6 empty] | 0
A-031 | 8 | 147-04-075 | 147-04-074 |  |  |  |  | HUMBER | Drive | [7 empty] | 0 | [6 empty] | 0
A-033 | 8 | 147-04-077 | 147-04-074 |  |  |  |  | TORBAY | Drive | [7 empty] | 0 | [6 empty] | 0
A-036 | 8 | 147-04-080 | 147-04-081 |  |  |  |  | WALLACE | Road | [7 empty] | 0 | [6 empty] | 0
A-037 | 8 | 147-04-081 | 147-04-082 |  |  |  |  | WALLACE | Road | [7 empty] | 0 | [6 empty] | 0
A-038 | 8 | 147-04-082 | RSSPSS25 |  |  |  |  | HUMBER | Drive | [7 empty] | 0 | [6 empty] | 0
A-039 | 8 | 147-04-084 | 147-04-085 |  |  |  |  | WALLACE | Road | [7 empty] | 0 | [6 empty] | 0
A-041 | 8 | 147-04-092 | 147-04-082 |  |  |  |  | HUMBER | Drive | [7 empty] | 0 | [6 empty] | 0
A-045 | 8 | 147-04-105 | 147-04-084 |  |  |  |  | WALLACE | Court | [7 empty] | 0 | [6 empty] | 0
A-047 | 8 | 147-08-011 | 147-08-010 |  |  |  |  | FAULKNER | Drive | [7 empty] | 0 | [6 empty] | 0
A-049 | 8 | 147-08-013 | 147-08-098 |  |  |  |  | FAULKNER | Drive | [7 empty] | 0 | [6 empty] | 0
A-050 | 8 | 147-08-014 | 147-08-015 |  |  |  |  | FAULKNER | Drive | [7 empty] | 0 | [6 empty] | 0
A-053 | 8 | 147-08-017 | 147-08-016 |  |  |  |  | FAULKNER | Drive | [7 empty] | 0 | [6 empty] | 0
A-054 | 8 | 147-08-018 | 147-08-019 |  |  |  |  | FAULKNER | Drive | [7 empty] | 0 | [6 empty] | 0
A-055 | 8 | 147-08-019 | 147-08-020 |  |  |  |  | FAULKNER | Drive | [7 empty] | 0 | [6 empty] | 0
A-056 | 8 | 147-08-020 | 147-08-021 |  |  |  |  | FAULKNER | Drive | [7 empty] | 0 | [6 empty] | 0
A-059 | 8 | 147-08-039 | 147-08-067 |  |  |  |  | TORBAY | Drive | [7 empty] | 0 | [6 empty] | 0
A-060 | 8 | 147-08-040 | 147-08-039 |  |  |  |  | WALES | Drive | [7 empty] | 0 | [6 empty] | 0
A-062 | 8 | 147-08-047 | 147-08-046 |  |  |  |  | HUMBER | Drive | [7 empty] | 0 | [6 empty] | 0
A-063 | 8 | 147-08-048 | 147-08-047 |  |  |  |  | HUMBER | Drive | [7 empty] | 0 | [6 empty] | 0
A-064 | 8 | 147-08-049 | 147-04-079 |  |  |  |  | TORBAY | Drive | [7 empty] | 0 | [6 empty] | 0
A-069 | 8 | 147-08-054 | 147-08-053 |  |  |  |  | WALES | Court | [7 empty] | 0 | [6 empty] | 0
A-070 | 8 | 147-08-055 | 147-08-054 |  |  |  |  | WALES | Court | [7 empty] | 0 | [6 empty] | 0
A-071 | 8 | 147-08-056 | 147-08-055 |  |  |  |  | WALES | Court | [7 empty] | 0 | [6 empty] | 0
A-072 | 8 | 147-08-057 | 147-08-056 |  |  |  |  | WALES | Court | [7 empty] | 0 | [6 empty] | 0
A-075 | 8 | 147-08-060 | 147-08-059 |  |  |  |  | WALES | Court | [7 empty] | 0 | [6 empty] | 0
A-076 | 8 | 147-08-061 | 147-08-060 |  |  |  |  | WALES | Court | [7 empty] | 0 | [6 empty] | 0
A-077 | 8 | 147-08-062 | 147-08-061 |  |  |  |  | WALES | Court | [7 empty] | 0 | [6 empty] | 0
A-078 | 8 | 147-08-063 | 147-08-062 |  |  |  |  | WALES | Drive | [7 empty] | 0 | [6 empty] | 0
A-083 | 8 | 147-08-068 | 147-08-067 |  |  |  |  | WALES | Drive | [7 empty] | 0 | [6 empty] | 0
A-086 | 8 | 147-08-071 | 147-08-070 |  |  |  |  | WALES | Drive | [7 empty] | 0 | [6 empty] | 0
A-088 | 8 | 147-08-073 | 147-08-071 |  |  |  |  | HOPEDALE | Drive | [7 empty] | 0 | [6 empty] | 0
A-093 | 8 | 147-08-078 | 147-08-077 |  |  |  |  | HUMBER | Drive | [7 empty] | 0 | [6 empty] | 0
A-097 | 8 | 147-08-082 | 147-08-074 |  |  |  |  | HOPEDALE | Drive | [7 empty] | 0 | [6 empty] | 0
A-098 | 8 | 147-08-096 | 147-08-100 |  |  |  |  | HOLLIS HILL | Drive | [7 empty] | 0 | [6 empty] | 0
A-100 | 8 | 147-08-098 | 147-08-012 |  |  |  |  | FAULKNER | Drive | [7 empty] | 0 | [6 empty] | 0
A-102 | 8 | 147-08-100 | 147-08-098 |  |  |  |  | HOLLIS HILL | Drive | [7 empty] | 0 | [6 empty] | 0
A-103 | 8 | 147-08-101 | 147-08-102 |  |  |  |  | HOLLIS HILL | Drive | [7 empty] | 0 | [6 empty] | 0
A-104 | 8 | 147-08-102 | 147-08-096 |  |  |  |  | HOLLIS HILL | Drive | [7 empty] | 0 | [6 empty] | 0
A-106 | 8 | 148-09-029 | 148-09-030 |  |  |  |  | FAULKNER | Drive | [7 empty] | 0 | [6 empty] | 0
A-108 | 8 | 147-12-043 | 147-12-064 |  |  |  |  | CARAWAY | Drive | [7 empty] | 0 | [6 empty] | 0
A-110 | 8 | 147-12-045 | 147-12-063 |  |  |  |  | CARAWAY | Drive | [7 empty] | 0 | [6 empty] | 0
A-111 | 8 | 147-12-046 | 147-08-040 |  |  |  |  | CARAWAY | Drive | [7 empty] | 0 | [6 empty] | 0
A-123 | 8 | 147-12-063 | 147-12-046 |  |  |  |  | CARAWAY | Drive | [7 empty] | 0 | [6 empty] | 0
A-124 | 8 | 147-12-064 | 147-12-044 |  |  |  |  | CARAWAY | Drive | [7 empty] | 0 | [6 empty] | 0
A-126 | 8 | 148-01-036 | 147-08-018 |  |  |  |  | TURLEY | Drive | [7 empty] | 0 | [6 empty] | 0
A-127 | 8 | 148-01-037 | 148-01-036 |  |  |  |  | TURLEY | Drive | [7 empty] | 0 | [6 empty] | 0
A-128 | 8 | 148-01-038 | 148-01-037 |  |  |  |  | TURLEY | Drive | [7 empty] | 0 | [6 empty] | 0
A-129 | 8 | 148-01-039 | 147-04-053 |  |  |  |  | WILLOW | Lane | [7 empty] | 0 | [6 empty] | 0
A-130 | 8 | 148-01-040 | 148-01-039 |  |  |  |  | WILLOW | Lane | [7 empty] | 0 | [6 empty] | 0
A-131 | 8 | 148-01-041 | 147-04-046 |  |  |  |  | WALLACE | Road | [7 empty] | 0 | [6 empty] | 0
A-132 | 8 | 148-01-042 | 148-01-041 |  |  |  |  | WALLACE | Road | [7 empty] | 0 | [6 empty] | 0
A-133 | 8 | 148-01-043 | 148-01-042 |  |  |  |  | TURLEY | Drive | [7 empty] | 0 | [6 empty] | 0
A-134 | 8 | 148-01-044 | 148-01-043 |  |  |  |  | TURLEY | Drive | [7 empty] | 0 | [6 empty] | 0
A-135 | 8 | 148-01-045 | 148-01-044 |  |  |  |  | TURLEY | Drive | [7 empty] | 0 | [6 empty] | 0
A-136 | 8 | 148-01-046 | 147-04-044 |  |  |  |  | WALLACE | Road | [7 empty] | 0 | [6 empty] | 0
A-137 | 8 | 148-01-047 | 148-01-046 |  |  |  |  | WALLACE | Road | [7 empty] | 0 | [6 empty] | 0
A-138 | 8 | 148-01-048 | 148-01-047 |  |  |  |  | WALLACE | Road | [7 empty] | 0 | [6 empty] | 0
A-139 | 8 | 148-01-072 | 148-01-048 |  |  |  |  | WALLACE | Road | [7 empty] | 0 | [6 empty] | 0
A-140 | 8 | 148-01-090 | 148-01-041 |  |  |  |  | WILLOW | Lane | [7 empty] | 0 | [6 empty] | 0
A-141 | 8 | 148-05-001 | 147-08-017 |  |  |  |  | LEOPOLE | Road | [7 empty] | 0 | [6 empty] | 0
A-142 | 8 | 148-05-002 | 148-05-001 |  |  |  |  | LEOPOLE | Road | [7 empty] | 0 | [6 empty] | 0
A-143 | 8 | 148-05-003 | 148-05-002 |  |  |  |  | LEOPOLE | Road | [7 empty] | 0 | [6 empty] | 0
A-144 | 8 | 148-05-004 | 147-08-017 |  |  |  |  | FAULKNER | Drive | [7 empty] | 0 | [6 empty] | 0
A-147 | 8 | 148-05-007 | 148-05-004 |  |  |  |  | LEOPOLE | Road | [7 empty] | 0 | [6 empty] | 0
A-149 | 8 | 148-05-009 | 148-05-008 |  |  |  |  | LEOPOLE | Road | [7 empty] | 0 | [6 empty] | 0
A-150 | 8 | 148-05-010 | 148-05-009 |  |  |  |  | TURLEY | Drive | [7 empty] | 0 | [6 empty] | 0
A-152 | 8 | 148-05-012 | 148-05-011 |  |  |  |  | TURLEY | Drive | [7 empty] | 0 | [6 empty] | 0
A-153 | 8 | 148-05-013 | 147-08-018 |  |  |  |  | TURLEY | Drive | [7 empty] | 0 | [6 empty] | 0
A-154 | 8 | 148-05-097 | 148-05-008 |  |  |  |  | TURLEY | Drive | [7 empty] | 0 | [6 empty] | 0
A-157 | 8 | 147-04-104 | 147-04-105 |  |  |  |  | WALLACE | Road | [7 empty] | 0 | [6 empty] | 0
A-201 | 8 | 107-05-010 | 107-05-009 |  |  |  |  | ELISSA/DABBS | Ave | [7 empty] | 0 | [6 empty] | 0
A-202 | 18 | 107-05-011 | 107-05-009 |  |  |  |  | ELISSA | Drive | [7 empty] | 0 | [6 empty] | 0
A-203 | 8 | 107-05-012 | 107-05-010 |  |  |  |  | ELISSA | Drive | [7 empty] | 0 | [6 empty] | 0
A-204 | 18 | 107-05-013 | 107-05-011 |  |  |  |  | ELISSA | Drive | [7 empty] | 0 | [6 empty] | 0
A-205 | 15 | 107-05-014 | 107-05-013 |  |  |  |  | ELISSA | Drive | [7 empty] | 0 | [6 empty] | 0
A-206 | 8 | 107-05-015 | 107-05-012 |  |  |  |  | PATRICIA | Drive | [7 empty] | 0 | [6 empty] | 0
A-207 | 8 | 107-05-020 | 107-05-015 |  |  |  |  | PATRICIA | Drive | [7 empty] | 0 | [6 empty] | 0
A-208 | 8 | 107-05-021 | 107-05-020 |  |  |  |  | KAREN | Drive | [7 empty] | 0 | [6 empty] | 0
A-209 | 8 | 107-05-022 | 107-05-021 |  |  |  |  | KAREN | Drive | [7 empty] | 0 | [6 empty] | 0
A-210 | 8 | 107-05-024 | 107-05-020 |  |  |  |  | PATRICIA | Drive | [7 empty] | 0 | [6 empty] | 0
A-211 | 8 | 107-05-025 | 107-05-021 |  |  |  |  | PATRICIA | Drive | [7 empty] | 0 | [6 empty] | 0
A-212 | 8 | 107-05-052 | 107-05-053 |  |  |  |  | PATRICIA | Drive | [7 empty] | 0 | [6 empty] | 0
A-213 | 8 | 107-05-054 | 107-05-014 |  |  |  |  | ELISSA | Drive | [7 empty] | 0 | [6 empty] | 0
A-214 | 8 | 107-05-077 | 107-05-024 |  |  |  |  | PATRICIA | Drive | [7 empty] | 0 | [6 empty] | 0
A-215 | 8 | 107-05-081 | 107-05-022 |  |  |  |  | KAREN | Drive | [7 empty] | 0 | [6 empty] | 0
A-216 | 8 | 107-05-082 | 107-05-081 |  |  |  |  | KAREN | Drive | [7 empty] | 0 | [6 empty] | 0
A-217 | 8 | 107-05-087 | 107-05-077 |  |  |  |  | PATRICIA | Drive | [7 empty] | 0 | [6 empty] | 0
A-218 | 8 | 107-09-039 | 107-005-083 |  |  |  |  | FIVE OAKS | Drive | [7 empty] | 0 | [6 empty] | 0
A-219 | 8 | 107-09-041 | 107-09-040 |  |  |  |  | MASSMAN | Drive | [7 empty] | 0 | [6 empty] | 0
A-220 | 8 | 107-09-042 | 107-09-041 |  |  |  |  | MASSMAN | Drive | [7 empty] | 0 | [6 empty] | 0
A-221 | 8 | 107-09-043 | 107-09-042 |  |  |  |  | MASSMAN | Drive | [7 empty] | 0 | [6 empty] | 0
A-222 | 8 | 107-09-044 | 107-09-043 |  |  |  |  | MASSMAN | Drive | [7 empty] | 0 | [6 empty] | 0
A-223 | 8 | 107-09-045 | 107-09-044 |  |  |  |  | MASSMAN | Drive | [7 empty] | 0 | [6 empty] | 0
A-224 | 8 | 107-09-046 | 107-09-045 |  |  |  |  | MASSMAN | Drive | [7 empty] | 0 | [6 empty] | 0
A-225 | 8 | 107-09-049 | 107-09-048 |  |  |  |  | MASSMAN | Drive | [7 empty] | 0 | [6 empty] | 0
A-226 | 12 | 107-10-015 | 107-10-002 |  |  |  |  | GLASTONBURY | BLVD | [7 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0
[17 empty] | 0 | [6 empty] | 0

## Manholes
Manhole Worksheet
Design Information | [6 empty] | Manhole Work Information | [6 empty] | Manhole Testing Information |  |  |  |  | Additional MH Bid Items
CWN Item No. | Manhole Number | Street Name | Sheet No. | Pipe Size | Plan Depth | Repair Code | EAC Depth | Type (Cem/epoxy) | Depth | Extra Depth | Dia. | Date Sprayed | Date Prepped | Date Tested | Gauge start | Gauge End | Pass/Fail | Comments | New Casting Install Date | Casting Type | Grout Date | Grout Qty | Sonde Locate Date | Date Raised | Depth Raised | Casting Adjustment Date | Casting Adjustment Depth
B-001 | 147-04-043 | WALLACE RD | 9/10 | 8 | 5.01 | G | 5.01 |  |  | 0
B-002 | 147-04-044 | WALLACE RD | 9/10 | 8 | 8.41 | C | 8.41 |  |  | 0
B-003 | 147-04-045 | FAULKNER DR | 9/10 | 8 | 6.36 | K | 6.36 |  |  | 0
B-006 | 147-04-048 | WALLACE RD | 9/10 | 8 | 17.2 | K | 17.2 |  |  | 0
B-007 | 147-04-049 | FAULKNER DR | 9/10 | 8 | 8.84 | L, C | 8.84 |  |  | 0
B-008 | 147-04-050 | FAULKNER DR | 9/10 | 8 | 6.92 | L; A1 | 6.92 |  |  | 0
B-009 | 147-04-051 | FAULKNER DR | 9/10 | 8 | 6.37 | H | 6.37 |  |  | 0 | [7 empty] | Smoke Defect at lid
B-010 | 147-04-052 | FAULKNER DR | 9/10 | 8 | 5.51 | L | 5.51 |  |  | 0
B-011 | 147-04-053 | WILLOW LN | 9/10 | 8 | 5.78 | L | 5.78 |  |  | 0
B-012 | 147-04-054 | FAULKNER DR | 9/10 | 8 | 5.47 | L | 5.47 |  |  | 0
B-015 | 147-04-057 | FAULKNER DR | 9/10 | 8 | 5.95 | L | 5.95 |  |  | 0
B-016 | 147-08-058 | FAULKNER DR | 13/14 | 8 | 5.07 | L | 5.07 |  |  | 0
B-017 | 147-04-061 | HOPEDALE DR | 9/10 | 8 | 6 | L | 6 |  |  | 0
B-018 | 147-04-062 | HOPEDALE DR | 9/10 | 8 | 7.1 | L | 7.1 |  |  | 0
B-019 | 147-08-063 | HOPEDALE DR | 13/14 | 8 | 9.88 | L | 9.88 |  |  | 0
B-020 | 147-04-064 | FOLEY DR | 9/10 | 8 | 8.5 | L | 8.5 |  |  | 0
B-021 | 147-04-065 | FOLEY DR | 9/10 | 8 | 8.5 | L | 8.5 |  |  | 0 | [7 empty] | PVC Drop
B-023 | 147-04-067 | FOLEY DR | 9/10 | 8 | 6.6 | G; L | 6.6 |  |  | 0
B-024 | 147-04-068 | HUMBER DR | 9/10 | 8 | 7 | L | 7 |  |  | 0
B-025 | 147-04-069 | HUMBER DR | 9/10 | 8 | 4.6 | L | 4.6 |  |  | 0
B-027 | 147-04-071 | FOLEY DR | 9/10 | 8 | 5.5 | L, A2 | 5.5 |  |  | 0
B-028 | 147-04-072 | FOLEY DR | 9/10 | 8 | 4.5 | L | 4.5 |  |  | 0
B-030 | 147-04-074 | TORBAY DR | 9/10 | 8 | 7.1 | G | 7.1 |  |  | 0
B-031 | 147-04-075 | HUMBER DR | 9/10 | 8 | 12 | H | 12 |  |  | 0
B-032 | 147-04-076 | HUMBER DR | 9/10 | 8 | 4.6 | L | 4.6 |  |  | 0
B-033 | 147-04-077 | TORBAY DR | 9/10 | 8 | 7 | L | 7 |  |  | 0
B-034 | 147-04-078 | TORBAY DR | 9/10 | 8 | 7.4 | L | 7.4 |  |  | 0
B-035 | 147-04-079 | TORBAY DR | 9/10 | 8 | 7.3 | L | 7.3 |  |  | 0
B-036 | 147-04-080 | WALLACE RD | 9/10 | 8 | 6.4 | K | 6.4 |  |  | 0
B-037 | 147-04-081 | WALLACE RD | 9/10 | 8 | 19.03 | K; C; UED | 19.03 |  |  | 0 | [7 empty] | PVC Drop Not Functional; Unplug existing drop
B-038 | 147-04-082 | HUMBER DR | 9/10 | 8 | 13.5 | K | 13.5 |  |  | 0 | [7 empty] | Inside SPS fence; Has lockable alum hatch; has exterior drop
B-039 | 147-04-084 | WALLACE RD | 9/10 | 8 | 6 | F | 6 |  |  | 0
B-040 | 147-04-085 | HUMBER DR | 9/10 | 8 | 8.7 | L | 8.7 |  |  | 0
B-041 | 147-04-092 | HUMBER DR | 9/10 | 8 | 11.7 | K | 11.7 |  |  | 0
B-042 | 147-04-093 | WALLACE RD | 9/10 | 8 | 10.5 | L; F | 10.5 |  |  | 0
B-043 | 147-04-094 | WALLACE RD | 9/10 | 8 | 5.25 | L | 5.25 |  |  | 0
B-044 | 147-04-095 | HOPEDALE DR | 9/10 | 8 | 7 | L | 7 |  |  | 0
B-047 | 147-08-011 | FAULKNER DR | 13/14 | 8 | 6.01 | H | 6.01 |  |  | 0
B-048 | 147-08-012 | FAULKNER DR | 13/14 | 8 | 5.07 | C | 5.07 |  |  | 0
B-049 | 147-08-013 | FAULKNER DR | 13/14 | 8 | 5.01 | L | 5.01 |  |  | 0
B-050 | 147-08-014 | FAULKNER DR | 13/14 | 8 | 5.26 | L | 5.26 |  |  | 0
B-051 | 147-08-015 | FAULKNER DR | 13/14 | 8 | 7.5 | C; L; G | 7.5 |  |  | 0
B-052 | 147-08-016 | FAULKNER DR | 13/14 | 8 | 5.29 | L | 5.29 |  |  | 0
B-053 | 147-08-017 | FAULKNER DR | 13/14 | 8 | 6.44 | L | 6.44 |  |  | 0
B-055 | 147-08-019 | FAULKNER DR | 13/14 | 8 | 4.96 | L | 4.96 |  |  | 0
B-056 | 147-08-020 | FAULKNER DR | 13/14 | 8 | 4.03 | L | 4.03 |  |  | 0
B-059 | 147-08-039 | TORBAY DR | 13/14 | 8 | 4.7 | L | 4.7 |  |  | 0
B-060 | 147-08-040 | TORBAY DR | 13/14 | 8 | 15.6 | L | 15.6 |  |  | 0
B-061 | 147-08-046 | HUMBER DR | 13/14 | 8 | 5.6 | G | 5.6 |  |  | 0
B-062 | 147-08-047 | HUMBER DR | 13/14 | 8 | 8.3 | L | 8.3 |  |  | 0
B-063 | 147-08-048 | HUMBER DR | 13/14 | 8 | 4 | L; A2 | 4 |  |  | 0
B-064 | 147-08-049 | TORBAY DR | 13/14 | 8 | 8.1 | L | 8.1 |  |  | 0
B-065 | 147-08-050 | TORBAY DR | 13/14 | 8 | 11.19 | L | 11.19 |  |  | 0
B-066 | 147-08-051 | TORBAY DR | 13/14 | 8 | 10.25 | L | 10.25 |  |  | 0
B-067 | 147-08-052 | TORBAY DR | 13/14 | 8 | 7.5 | L | 7.5 |  |  | 0
B-068 | 147-08-053 | TORBAY DR | 13/14 | 8 | 4.6 | L | 4.6 |  |  | 0
B-069 | 147-08-054 | WALES CT | 13/14 | 8 | 12.6 | L | 12.6 |  |  | 0
B-070 | 147-08-055 | WALES CT | 13/14 | 8 | 5.1 | L | 5.1 |  |  | 0
B-071 | 147-08-056 | WALES CT | 13/14 | 8 | 6.5 | L; G | 6.5 |  |  | 0
B-072 | 147-08-057 | WALES CT | 13/14 | 8 | 7.11 | L | 7.11 |  |  | 0
B-073 | 147-08-058 | WALES CT | 13/14 | 8 | 10.51 | G | 10.51 |  |  | 0
B-074 | 147-08-059 | TORBAY DR | 13/14 | 8 | 9.1 | L | 9.1 |  |  | 0 | [7 empty] | MH prevkiously lined w Epoxy
B-075 | 147-08-060 | WALES CT | 13/14 | 8 | 13.1 | L | 13.1 |  |  | 0 | [7 empty] | PVC Drop
B-076 | 147-08-061 | WALES CT | 13/14 | 8 | 4.1 | A2 | 4.1 |  |  | 0
B-077 | 147-08-062 | WALES CT | 13/14 | 8 | 5.6 | A2 | 5.6 |  |  | 0
B-079 | 147-08-064 | TORBAY DR | 13/14 | 8 | 9.5 | L | 9.5 |  |  | 0
B-080 | 147-08-065 | TORBAY DR | 13/14 | 8 | 9.6 | L | 9.6 |  |  | 0
B-081 | 147-08-066 | TORBAY DR | 13/14 | 8 | 7.6 | L | 7.6 |  |  | 0
B-082 | 147-08-067 | TORBAY DR | 13/14 | 8 | 7.6 | L; G | 7.6 |  |  | 0
B-084 | 147-08-069 | WALES DR | 13/14 | 8 | 7.6 | L; H | 7.6 |  |  | 0
B-085 | 147-08-070 | WALES DR | 13/14 | 8 | 9.5 | L; G | 9.5 |  |  | 0
B-086 | 147-08-071 | WALES DR | 13/14 | 8 | 8.1 | L | 8.1 |  |  | 0
B-087 | 147-08-072 | HOPEDALE DR | 13/14 | 8 | 9 | H | 9 |  |  | 0
B-088 | 147-08-073 | HOPEDALE DR | 13/14 | 8 | 8.6 | K | 8.6 |  |  | 0 | [7 empty] | MH previously lined w Epoxy. Some staining is evident.
B-089 | 147-08-074 | HOPEDALE DR | 13/14 | 8 | 4.1 | L; H | 4.1 |  |  | 0
B-090 | 147-08-075 | HOPEDALE DR | 13/14 | 8 | 5.1 | L | 5.1 |  |  | 0 | [7 empty] | PVC Drop
B-091 | 147-08-076 | HUMBER DR | 13/14 | 8 | 8 | L; G | 8 |  |  | 0
B-092 | 147-08-077 | HUMBER DR | 13/14 | 8 | 5.3 | L | 5.3 |  |  | 0
B-093 | 147-08-078 | HUMBER DR | 13/14 | 8 | 7.6 | L; H | 7.6 |  |  | 0
B-094 | 147-08-079 | HUMBER DR | 13/14 | 8 | 4.2 | L | 4.2 |  |  | 0
B-097 | 147-08-082 | HOPEDALE DR | 13/14 | 8 | 11.1 | K; G | 11.1 |  |  | 0 | [7 empty] | Line w epoxy due to proximity to SPS
B-098 | 147-08-096 | HOLLIS HILL DR | 13/14 | 8 | 6.38 | G | 6.38 |  |  | 0
B-100 | 147-08-098 | FAULKNER DR | 13/14 | 8 | 4.82 | L | 4.82 |  |  | 0
B-101 | 147-08-099 | HOLLIS HILL DR | 13/14 | 8 | 18.11 | L | 18.11 |  |  | 0 | [7 empty] | Drop Present
B-103 | 147-08-101 | HOLLIS HILL DR | 13/14 | 8 | 19.06 | L | 19.06 |  |  | 0
B-104 | 147-08-102 | HOLLIS HILL DR | 13/14 | 8 | 11.94 | L | 11.94 |  |  | 0
B-108 | 147-12-043 | HOLLIS HILL DR | 17/18 | 8 | 4.94 | N | 4.94 |  |  | 0 | [7 empty] | Recheck downstream line to ensure no services. If none, then abandon & remove MH.. Plug downstream pipe. See plans.
B-109 | 147-12-044 | HAYWOOD LN | 17/18 | 8 | 6.2 | C; L | 6.2 |  |  | 0
B-110 | 147-12-045 | HAYWOOD LN | 17/18 | 8 | 4.46 | G | 4.46 |  |  | 0
B-113 | 147-12-048 | HOPEDALE DR | 17/18 | 8 | 13.5 | L | 13.5 |  |  | 0
B-115 | 147-12-052 | HOLLIS HILL DR | 17/18 | 8 | 11.46 | L | 11.46 |  |  | 0
B-119 | 147-12-057 | HOPEDALE DR | 17/18 | 8 | 10 | L | 10 |  |  | 0
B-122 | 147-12-062 | CARAWAY LANE | 17/18 | 8 | 7.29 | L | 7.29 |  |  | 0
B-123 | 147-12-063 | CARAWAY LANE | 17/18 | 8 | 4.85 | A2 | 4.85 |  |  | 0
B-124 | 147-12-064 | CARAWAY LANE | 17/18 | 8 | 2.68 | P | 2.68 |  |  | 0 | [7 empty] | Plug line from 147-12-043 after verifying that no services are on upstream line.
B-126 | 148-01-036 | TURLEY DR | 11/12 | 8 | 6.7 | L | 6.7 |  |  | 0
B-127 | 148-01-037 | TURLEY DR | 11/12 | 8 | 7 | L | 7 |  |  | 0
B-128 | 148-01-038 | TURLEY DR | 11/12 | 8 | 5.62 | L | 5.62 |  |  | 0
B-129 | 148-01-039 | WILLOW LN | 11/12 | 8 | 5.28 | L | 5.28 |  |  | 0
B-130 | 148-01-040 | WILLOW LN | 11/12 | 8 | 5.15 | L | 5.15 |  |  | 0
B-131 | 148-01-041 | WALLACE RD | 11/12 | 8 | 5.55 | L; F; G | 5.55 |  |  | 0
B-132 | 148-01-042 | WALLACE RD | 11/12 | 8 | 9.09 | C; G | 9.09 |  |  | 0
B-133 | 148-01-043 | TURLEY DR | 11/12 | 8 | 10.79 | L | 10.79 |  |  | 0
B-134 | 148-01-044 | TURLEY DR | 11/12 | 8 | 7.1 | L; G | 7.1 |  |  | 0
B-135 | 148-01-045 | TURLEY DR | 11/12 | 8 | 5.55 | L | 5.55 |  |  | 0
B-140 | 148-01-090 | WILLOW LN | 11/12 | 8 | 10.53 | L | 10.53 |  |  | 0
B-142 | 148-05-002 | LEOPOLE RD | 15/16 | 8 | 6.88 | L | 6.88 |  |  | 0
B-143 | 148-05-003 | LEOPOLE RD | 15/16 | 8 | 6.54 | N | 6.54 |  |  | 0 | [7 empty] | Abandon MH and add new MH aprox 15' downstream. See plans
B-144 | 148-05-004 | FAULKNER DR | 15/16 | 8 | 6.68 | L | 6.68 |  |  | 0
B-145 | 148-05-005 | FAULKNER DR | 15/16 | 8 | 8.46 | L | 8.46 |  |  | 0
B-146 | 148-05-006 | FAULKNER DR | 15/16 | 8 | 8.07 | L | 8.07 |  |  | 0
B-147 | 148-05-007 | LEOPOLE RD | 15/16 | 8 | 4.68 | L | 4.68 |  |  | 0
B-148 | 148-05-008 | LEOPOLE RD | 15/16 | 8 | 9.15 | F; G | 9.15 |  |  | 0 | [7 empty] | Drop
B-152 | 148-05-012 | TURLEY DR | 15/16 | 8 | 5.09 | L | 5.09 |  |  | 0
B-153 | 148-05-013 | TURLEY DR | 15/16 | 8 | 5.83 | L | 5.83 |  |  | 0
B-154 | 148-05-097 | TURLEY DR | 15/16 | 8 | 5.2 | L | 5.2 |  |  | 0
B-155 | 148-05-098 | FAULKNER DR | 15/16 | 8 | 4.86 | L | 4.86 |  |  | 0
B-156 | 148-09-030 | FAULKNER PLACE | 19/20 | 8 | 5.02 | L; G | 5.02 |  |  | 0
B-157 | 148-09-029 | FAULKNER DR | 19/20 | 8 | 5 | L | 5 |  |  | 0
B-201 | 107-05-009 | PATRICIA DR | 25/26 |  | 6.6 | L | 6.6 |  |  | 0
B-202 | 107-05-010 | PATRICIA DR | 25/26 |  | 3.87 | L | 3.87 |  |  | 0
B-203 | 107-05-011 | PATRICIA DR | 25/26 |  | 6.4 | L | 6.4 |  |  | 0
B-204 | 107-05-012 | PATRICIA DR | 25/26 |  | 4 | L, G | 4 |  |  | 0
B-205 | 107-05-013 | ELISSA DR | 25/26 |  | 6.2 | L | 6.2 |  |  | 0
B-206 | 107-05-014 | ELISSA DR | 25/26 |  | 6.9 | L | 6.9 |  |  | 0
B-207 | 107-05-015 | PATRICIA DR | 25/26 |  | 6.44 | L, M | 6.44 |  |  | 0
B-208 | 107-05-020 | PATRICIA DR | 25/26 |  | 11.14 | L,F | 11.14 |  |  | 0
B-209 | 107-05-021 | PATRICIA DR | 25/26 |  | 8.4 | L, M | 8.4 |  |  | 0
B-210 | 107-05-022 | KAREN DR | 25/26 |  | 7.27 | L | 7.27 |  |  | 0
B-211 | 107-05-024 | PATRICIA DR | 25/26 |  | 6.94 | L, M | 6.94 |  |  | 0
B-212 | 107-05-025 | PATRICIA DR | 25/26 |  | 10.34 | L | 10.34 |  |  | 0 | [7 empty] | DROP
B-213 | 107-05-052 | ELISSA DR | 25/26 |  | 6.96 | L | 6.96 |  |  | 0
B-214 | 107-05-053 | ELISSA DR | 25/26 |  | 4.2 | L | 4.2 |  |  | 0
B-215 | 107-05-054 | ELISSA DR | 25/26 |  | 6.59 | L | 6.59 |  |  | 0 | [7 empty] | DROP X 2
B-216 | 107-05-077 | PATRICIA DR | 25/26 |  | 15.4 | L, F | 15.4 |  |  | 0 | [7 empty] | DROP
B-217 | 107-05-081 | MASSMAN DR | 25/26 |  | 3.15 | L, G, P, F | 3.15 |  |  | 0 | [7 empty] | PLUG ORIGINAL STUBOUT TO NW
B-218 | 107-05-082 | OAK GROVE DR | 25/26 |  | 5.36 | L | 5.36 |  |  | 0
B-219 | 107-05-083 | FIVE OAKS DR | 25/26 |  | 3.06 | L | 3.06 |  |  | 0
B-220 | 107-09-003 | MASSMAN DR | 25/26 |  | 4.84 | L, G | 4.84 |  |  | 0
B-221 | 107-09-039 | MASSMAN DR | 27/28 |  | 11.66 | L, F | 11.66 |  |  | 0 | [7 empty] | DROP
B-222 | 107-09-040 | MASSMAN DR | 27/28 |  | 3.55 | L | 3.55 |  |  | 0
B-223 | 107-09-041 | MASSMAN DR | 27/28 |  | 4.2 | L | 4.2 |  |  | 0
B-224 | 107-09-042 | MASSMAN DR | 27/28 |  | 4.75 | L, C | 4.75 |  |  | 0 | [7 empty] | DAYLIGHT SHOWING AT PICK HOLE-FRAME BROKE
B-225 | 107-09-043 | MASSMAN DR | 27/28 |  | 4.05 | L | 4.05 |  |  | 0 | [7 empty] | AS BUILTS NOTE STUB FOR 1014 MASSMAN IN MH
B-226 | 107-09-044 | MASSMAN DR | 27/28 |  | 5.85 | L | 5.85 |  |  | 0
B-227 | 107-09-045 | MASSMAN DR | 27/28 |  | 4.5 | L, H | 4.5 |  |  | 0
B-228 | 107-09-046 | MASSMAN DR | 27/28 |  | 7.35 | L | 7.35 |  |  | 0
B-229 | 107-09-048 | MASSMAN DR | 27/28 |  | 4.06 | L | 4.06 |  |  | 0
B-230 | 107-09-049 | MASSMAN DR | 27/28 |  | 4.62 | L, M | 4.62 |  |  | 0
B-231 | 107-10-002 | GLASTONBURY BLVD | 29/30 |  | 6.4 | L | 6.4 |  |  | 0
B-232 | 107-10-015 | GLASTONBURY BLVD | 29/30 |  | 3.22 | K, M | 3.22 |  |  | 0 | [7 empty] | MH IS A SPECIAL SHALLOW TYPE
[7 empty] | 0 |  |  | 0

## Hard Surface Restoration
Hard Surface Restoration
Design Information | [7 empty] | Dimensions |  |  | Calculated Quantities |  |  | Asphalt Restoration | [6 empty] | Concrete Restoration
CWN Item No. | Pipe Dia. | Upstream MH | Downstream MH | Distance from US MH | Clock Position | House # | Street Name | Length (ft) | Width (ft) | Depth (ft) | SY | CY | Calculated Tonnage | Date Binder Installed | Quantity Binder (Ton) | Date Milled | Quantity Milled (SY) | Date Paved | Quantity Paved (Ton) | Driveway or Roadway | Date Installed | Qty Installed (SY) | Driveway or Sidewalk | Flow Fill Qty (CY) | Concrete Encasement (CY) | Concrete Curb Qty (LF) | Pay Item(s) | Comments
[11 empty] | 0 | 0 | 0
[11 empty] | 0 | 0 | 0
[11 empty] | 0 | 0 | 0
[11 empty] | 0 | 0 | 0
[11 empty] | 0 | 0 | 0
[11 empty] | 0 | 0 | 0
[11 empty] | 0 | 0 | 0
[11 empty] | 0 | 0 | 0
[11 empty] | 0 | 0 | 0
[11 empty] | 0 | 0 | 0
[11 empty] | 0 | 0 | 0
[11 empty] | 0 | 0 | 0
[11 empty] | 0 | 0 | 0
[11 empty] | 0 | 0 | 0
[11 empty] | 0 | 0 | 0
[11 empty] | 0 | 0 | 0
[11 empty] | 0 | 0 | 0
[11 empty] | 0 | 0 | 0
[11 empty] | 0 | 0 | 0
[11 empty] | 0 | 0 | 0

## Point Repairs
Point Repairs
Design Information | [7 empty] | Excavation Repairs | [9 empty] | CIPP Repairs
CWN Item No. | Pipe Dia. | Upstream MH | Downstream MH | Distance from US MH | Clock Position | House # | Street Name | Excavation Length (ft) | Excavation Width (ft) | Excavation Depth (ft) | Date Installed | Pipe Length (FT) | Pipe Depth (FT) | Concrete Encasement (CY) | Flowable Fill (SY) | Service or Mainline | Inside Paved Area? | Date Installed | Length (FT) | Comments

## Misc Bid Items
Misc Bid Items
Design Information | [8 empty] | Repair Details
CWN Item No. | Pipe Dia. | Sheet # | Upstream MH | Downstream MH | Distance from US MH | Clock Position | House # | Street Name | Date Installed | Repair Description | Repair Qty | Pay Item(s) | Comments
C-1 | 8 | 9/10/11/12 | 147-01-046 | 147-04-044 | 373 |  | 264 | Wallace Road |  | Provide new cleanout cap |  |  | Smoke coming from CO with missing cap | Yard
C-2 | 8 | 13/14 | 147-08-016 | 147-08-015 | 261 |  | 3740 | Faulkner Dr |  | Repair cleanout assembly |  |  | Smoke coming from cleanout box | Yard
C-3 | 8 | 13/14 | 147-08-012 | 147-08-011 | 341 |  | 3743 | Faulkner Dr |  | Repair cleanout assembly |  |  | Smoke coming from broken cleanout | Yard
C-4 | 8 | 13/14 | 147-08-012 | 147-08-011 | 341 |  | 3739 | Faulkner Dr |  | Repair cleanout assembly & box |  |  | Smoke coming from broken cleanout with broken lid | Yard
C-5 | 8 | 13/14 | 147-08-011 | 147-08-010 | 381 |  | 3737 | Faulkner Dr |  | Repair cleanout assembly |  |  | Smoke coming from broken cleanout | Yard
C-6 | 8 | 15/16 | 148-05-005 | 148-05-004 | 198 |  | 3764 | Faulkner Dr |  | Repair cleanout assembly |  |  | Smoke coming from cleanout box | Exposed Aggregate Concrete Drive
C-7 | 8 | 15/16 | 148-05-006 | 148-05-005 | 298 |  | 3800 | Faulkner Dr |  | Repair cleanout assembly |  |  | Smoke coming from cleanout box | Yard
C-8 | 8 | 13/14 | 147-08-097 | 147-08-099 | 351 |  | 4081 | Hollis Hill Dr |  | Replace existing cleanout cap |  |  | Smoke coming from cleanout with missing cap | Yard
C-9 | 8 | 13/14 | 147-08-096 | 147-08-100 | 173 |  | 4088 | Hollis Hill Dr |  | Repair cleanout assembly |  |  | Smoke coming from cleanout adjacent to fdn | Yard
C-10 | 8 | 13/14 | 147-08-102 | 147-08-096 | 204 |  | 4084 | Hollis Hill Dr |  | Remove defective stack piece; lower cleanout cap to grade and place in box |  |  | Smoke from broken cleanout stack | Yard
C-11 | 8 | 13/14/17/18 | 147-12-053 | 147-08-099 | 278 |  | 4053 | Hollis Hill Dr |  | Replace existing cleanout cap |  |  | Smoke coming from cleanout with missing cap | Yard
C-12 | 8 | 13/14 | 147-08-070 | 147-08-069 | 163 |  | 357 | Wales Dr |  | Replace existing cleanout cap |  |  | Smoke coming from cleanout with missing cap | Yard
C-13 | 8 | 13/14 | 147-08-061 | 147-08-060 | 255 |  | 4802 | Wales Ct |  | Replace existing cleanout cap |  |  | Smoke coming from cleanout with missing cap | Yard
C-14 | 8 | 9/10/11/12 | 148-01-039 | 147-04-053 | 196 |  | 259 | Willow Dr |  | Replace existing solid cleanout cap |  |  | Smoke coming from slotted cleanout cap | Yard
C-15 | 8 | 9/10 | 147-04-054 | 147-04-052 | 123 |  | 3710 | Faulkner Dr |  | CCTV lateral and confirm defect. Repair cleanout assembly |  |  | Smoke coming from below cleanout cap | Yard
C-16 | 8 | 9/10 | 147-04-054 | 147-04-052 | 123 |  | 3710 | Faulkner Dr |  | CCTV lateral and confirm defect. Repair cleanout assembly |  |  | Smoke coming from cleanout adjacent to fdn | Yard
C-17 | 8 | 9/10/13/14 | 147-08-049 | 147-04-079 | 269 |  | 4824 | Torbay |  | CCTV lateral and confirm defect. Repair lateral defect(s) |  |  | Smoke coming from lateral | Yard
C-18 | 8 | 13/14 | 147-08-080 | 147-08-081 | 255 |  | 4831 | Hopedale Dr |  | Replace existing cleanout cap |  |  | Smoke coming from cleanout with missing cap | Yard
C-19 | 8 | 15/16/19/20 | 148-09-030 | 148-05-098 | 350 |  | 3849 | Faulkner Dr |  | Replace existing solid cleanout cap |  |  | Smoke coming from slotted cleanout cap | Yard
C-20 | 8 | 15/16 | 148-05-006 | 148-05-005 | 298 |  | 3809 | Faulkner Dr |  | Replace broken cleanout lid |  |  | Smoke coming from cleanout box | Exposed Aggregate Concrete Drive
C-21 | 8 | 17/18 | 147-12-055 | 147-12-054 | 275 |  | 4001 | Hollis Hill Dr |  | Replace broken cleanout lid |  |  | Smoke coming from broken cleanout | Yard
C-22 | 8 | 17/18 | 147-12-055 | 147-12-054 | 275 |  | 4005 | Hollis Hill Dr |  | Replace broken cleanout lid |  |  | Smoke coming from broken cleanout | Yard
C-23 | 8 | 17/18 | 147-12-054 | 147-12-052 | 146 |  | 4017 | Hollis Hill Dr |  | Replace existing cleanout cap |  |  | Smoke coming from cleanout with missing cap | Yard
C-24 | 8 | 17/18 | 147-12-054 | 147-12-052 | 146 |  | 4016 | Hollis Hill Dr |  | Repair cleanout assembly |  |  | Smoke coming from broken cleanout | Yard
C-24 | 8 | 17/18 | 147-12-052 | 147-12-051 | 296 |  | 4029 | Hollis Hill Dr |  | Replace broken cleanout lid |  |  | Smoke coming from broken cleanout | Yard
C-25 | 8 | 13/14/17/18 | 147-12-057 | 147-08-073 | 315 |  | 4929 | Hopedale Dr |  | Replace existing cleanout cap |  |  | Smoke coming from cleanout with missing cap | Yard

## Lists
CWN Recommendations - Service Tab | Tie In Material | Abbreviations for Sheet C-2
Abandon/Line over | Clay | C | Capped
Blind Shot | Concrete | UNK | Unknown
Blind Shot & Tophat | Metal | R | Right
CIPP with C/O | PVC | L | Left
Cleanout Only |  | CCTV | Closed Circuit Television
Cut and Brush |  | PVC | Polyvinyl Chloride
Drop Connection |  | CIPP | Cured-In-Place-Pipe
Line to Existing |  | VCP | Vitrified Clay Pipe
No Action |  | EX | External Point Repair
Other, See Notes |  | IR | Internal Main Line CIPP Point Repair
Service Relay |  | SD | Smoke Defect
Tophat |  | JC | Jet Cleaning
Transition |  | FM | Force Main
|  | SR-U | Service Repair - Unknown Repair Method, determine in field with Construction Manager
|  | SR-PR | Service Repair - External Point Repair
|  | SR-LL | Service Repair - Lateral Lining
|  | CO-A | Cleanout Cap Repair - Install cleanout box and threaded PVC cleanout adapter with plug including any necessary fittings required for re-connecting to existing pipe
|  | CO-B | Cleanout Assembly Repair - Replace tee wye and vertical cleanout sewer pipe to grade including new cleanout adapter and cleanout box
|  | N/A | Not applicable
|  | MH | Manhole
|  | DIP | Ductile Iron Pipe
|  | DSMH | Downstream Manhole
|  | USMH | Upstream Manhole
|  | P | Plug abandoned sewer line from inside MH