## Mainline
Mainline Liner
Design Information | [10 empty] | Pre CCTV Information | [13 empty] | Liner Installation Information |  |  |  |  | Liner Testing Information |  |  |  | Post CCTV Information
CWN Item No. | SAC | SAC Revised | Existing Pipe Material | USMH | DSMH | Pipe Dia. | Street Name | Sheet No. | Plan Length | EAC Length | Pre CCTV Date | Camera Direction | Hard Tape Length | CCTV Length | Service Count | US MH Depth | US MH Diameter | DS MH Depth | DS MH Diameter | Mainline Material | Heavy Cleaning Length | Status | Bid Item Number | Pre-TV Notes | Date Installed | Installed Length | Contractor Shot No. | # of Services | Drop | Air Test? | Test PSI Start | Test PSI End | Air Test Pass/Fail | Post CCTV Date | Uploaded to MWS Date | Comments
A-001 | CCTV, JC | CCTV, JC | CIPP | 147-04-043 | 147-04-044 | 8 | WALLACE RD | 9/10 | 78 | 78 | 2026-04-03 | Downstream | 78 | 77.3 | 2 | 4' | 8" | 8.2' | 8" | CIPP | NA | Previously Lined | B-3 |  |  | 0 |  | 1
A-002 | CIPP | CIPP | VCP | 147-04-044 | 147-04-045 | 8 | FAULKNER DR | 9/10 | 158 | 160 | 2026-04-02 | Upstream | 160 | 159.8 | 0 | 8.2' | 8" | 6.5' | 8" | VCP | NA | Ready to Line | B-3 |  |  | 0 |  | 0
A-003 | CIPP | CIPP | VCP | 147-04-045 | 147-04-047 | 8 | FAULKNER DR | 9/10 | 38 | 38 | 2026-04-02 | Upstream | 38 | 37.1 | 0 | 6.5' | 8" | 6.7' | 8" | VCP | NA | Ready to Line | B-3 |  |  | 0 |  | 0
A-005 | CCTV | CCTV | CIPP | 147-04-047 | 147-04-048 | 8 | FAULKNER DR | 9/10 | 65 | 67 | 2026-04-03 | Downstream | 67 | 66.6 | 0 | 6.7' | 8" | 12' | 8" | CIPP | NA | Previously Lined | B-3 |  |  | 0 |  | 0
A-006 | CCTV, JC | CCTV, JC | CIPP | 147-04-048 | 147-04-049 | 8 | WALLACE RD | 9/10 | 127 | 127 | [15 empty] | 0 |  | 1
A-007 | CCTV, JC | CCTV, JC | CIPP | 147-04-049 | 147-04-093 | 8 | FAULKNER DR | 9/10 | 143 | 143 | [15 empty] | 0 |  | 1
A-009 | CCTV, JC | CCTV, JC | CIPP | 147-04-051 | 147-04-049 | 8 | FAULKNER DR | 9/10 | 84 | 84 | [15 empty] | 0 |  | 1
A-010 | CIPP | CIPP | VCP | 147-04-052 | 147-04-050 | 8 | FAULKNER DR | 9/10 | 167 | 167 | 2026-04-02 | Downstream | 167 | 166.7 | 2 | 5.5' | 8" | 7.2' | 8" | VCP | NA | Ready to Line | B-3 |  |  | 0 |  | 2
A-011 | CIPP | CIPP | VCP | 147-04-053 | 147-04-052 | 8 | WILLOW LN | 9/10 | 203 | 202 | 2026-04-02 | Upstream | 202 | 201.4 | 1 | 5.9' | 8" | 5.5' | 8" | VCP | NA | Needs Attention | B-3 | 72.8' TOTAL FEET OF PIPE HAS DEEP CRACKS AND BROKEN AREAS / FROM 93.3'-166.1' FROM DSMH 147-04-052 |  | 0 |  | 2
A-012 | CIPP | CIPP | VCP | 147-04-054 | 147-04-052 | 8 | FAULKNER DR | 9/10 | 123 | 122 | 2026-04-02 | Upstream | 122 | 121.9 | 0 | 6' | 8" | 5.5' | 8" | VCP | NA | Ready to Line | B-3 |  |  | 0 |  | 0
A-013 | CCTV; IR (3) | CCTV; IR (3) | CIPP | 147-04-055 | 147-04-051 | 8 | FAULKNER DR | 9/10 | 332 | 332 | [15 empty] | 0 |  | 4
A-014 | IR (1) | CCTV; IR (1) | CIPP | 147-04-056 | 147-04-055 | 8 | FAULKNER DR | 9/10 | 115 | 115 | [15 empty] | 0 |  | 2
A-015 | CIPP | CIPP | VCP | 147-04-057 | 147-04-054 | 8 | FAULKNER DR | 9/10 | 269 | 270 | 2026-04-02 | Upstream | 270 | 269.8 | 4 | BURIED | NA | 6' | 8" | VCP | NA | Needs Attention | B-3 | USMH 147-04-057 / BURIED - SONDE/LOCATED MARKED IN ROAD 7' DEEP |  | 0 |  | 4
A-016 | CIPP | CIPP | VCP | 147-04-058 | 147-08-014 | 8 | FAULKNER DR | 9/10/13/14 | 320 | 320 | [15 empty] | 0 |  | 5
A-024 | S-LTV | S-LTV | PVC | 147-04-068 | 147-04-085 | 8 | HUMBER DR | 9/10 | 125 | 125 | [15 empty] | 0 |  | 1
A-025 | CCTV, JC | CCTV, JC | PVC | 147-04-069 | 147-04-068 | 8 | HUMBER DR | 9/10 | 278 | 278 | [15 empty] | 0 |  | 3
A-026 | CCTV, JC | CCTV, JC | PVC | 147-04-070 | 147-04-069 | 8 | FOLEY DR | 9/10 | 255 | 255 | [15 empty] | 0 |  | 2
A-027 | CCTV | CCTV | DIP | 147-04-071 | 147-04-070 | 8 | FOLEY DR | 9/10 | 73 | 74 | 2026-04-06 | Downstream | 74 | 73.1 | 0 | 11' | 8" | 5.4' | 8" | Concrete | NA | Ready to Line | B-3 |  |  | 0 |  | 0
A-028 | CCTV | CCTV | PVC | 147-04-072 | 147-04-071 | 8 | FOLEY DR | 9/10 | 98 | 102 | 2026-04-06 | Upstream | 102 | 101.5 | 1 | 4.5' | 8" | 5.4' | 8" | PVC | NA | Ready to Line | B-3 |  |  | 0 |  | 2
A-029 | CCTV, JC | CCTV, JC | DIP | 147-04-073 | 147-04-081 | 8 | TORBAY DR | 9/10 | 258 | 258 | [15 empty] | 0 |  | 1
A-030 | CCTV, JC | CCTV, JC | PVC | 147-04-074 | 147-04-073 | 8 | TORBAY DR | 9/10 | 115 | 113 | 2026-04-06 | Downstream | 113 | 112.2 | 1 | 7.7' | 8" | 9.5' | 8" | PVC | NA | Ready to Line | B-3 |  |  | 0 |  | 1
A-031 | CCTV, JC | CCTV, JC | PVC | 147-04-075 | 147-04-074 | 8 | HUMBER DR | 9/10 | 193 | 194 | 2026-04-06 | Upstream | 194 | 193.5 | 0 | 12' | 8" | 7.7' | 8" | PVC | NA | Ready to Line | B-3 |  |  | 0 |  | 0
A-033 | CCTV, JC | CCTV, JC | PVC | 147-04-077 | 147-04-074 | 8 | TORBAY DR | 9/10 | 125 | 124 | 4/6/226 | Downstream | 124 | 123.2 | 2 | 7.8' | 8" | 7.7' | 8" | PVC | NA | Ready to Line | B-3 |  |  | 0 |  | 2
A-036 | CCTV, JC | CCTV, JC | PVC | 147-04-080 | 147-04-081 | 8 | WALLACE RD | 9/10 | 82 | 82 | [15 empty] | 0 |  | 1
A-037 | CCTV, JC | CCTV, JC | DIP | 147-04-081 | 147-04-082 | 8 | WALLACE RD | 9/10 | 177 | 177 | [15 empty] | 0 |  | 2
A-038 | CCTV | CCTV | PVC | 147-04-082 | RSSPSS25 | 8 | HUMBER DR | 9/10 | 26 | 26 | [15 empty] | 0 |  | 0
A-039 | CCTV | CCTV | PVC | 147-04-084 | 147-04-085 | 8 | WALLACE RD | 9/10 | 139 | 139 | [15 empty] | 0 |  | 0
A-041 | CCTV, JC | CCTV, JC | PVC | 147-04-092 | 147-04-082 | 8 | HUMBER DR | 9/10 | 83 | 83 | [15 empty] | 0 |  | 0
A-045 | CCTV | CCTV | PVC | 147-04-105 | 147-04-084 | 8 | WALLACE COURT | 9/10 | 45 | 45 | [15 empty] | 0 |  | 0
A-047 | S-PR, IR (2) | CCTV; S-PR, IR (2) | CIPP | 147-08-011 | 147-08-010 | 8 | FAULKNER DR | 13/14 | 381 | 381 | [15 empty] | 0 |  | 5
A-049 | CIPP; S-PR(2), IR (4) | CIPP | VCP | 147-08-013 | 147-08-098 | 8 | FAULKNER DR | 13/14 | 94 | 94 | [15 empty] | 0 |  | 2
A-050 | CIPP | CIPP | VCP | 147-08-014 | 147-08-015 | 8 | FAULKNER DR | 13/14 | 293 | 293 | [15 empty] | 0 |  | 4
A-053 | S-LTV (1) | S-LTV (1) | CIPP | 147-08-017 | 147-08-016 | 8 | FAULKNER DR | 13/14 | 283 | 283 | [15 empty] | 0 |  | 2
A-054 | CIPP, S-PR (4), IR (8) | CIPP | VCP | 147-08-018 | 147-08-019 | 8 | FAULKNER DR | 13/14 | 226 | 226 | [15 empty] | 0 |  | 4
A-055 | CIPP, S-PR (2), IR (4) | CIPP | VCP | 147-08-019 | 147-08-020 | 8 | FAULKNER DR | 13/14 | 241 | 241 | [15 empty] | 0 |  | 2
A-056 | CIPP, S-PR (2), IR (4) | CIPP | VCP | 147-08-020 | 147-08-021 | 8 | FAULKNER DR | 13/14 | 119 | 119 | [15 empty] | 0 |  | 4
A-059 | CCTV | CCTV | PVC | 147-08-039 | 147-08-067 | 8 | TORBAY DR | 13/14 | 31 | 31 | [15 empty] | 0 |  | 0
A-060 | CCTV, JC | CCTV, JC | DIP | 147-08-040 | 147-08-039 | 8 | WALES DR | 13/14 | 100 | 100 | [15 empty] | 0 |  | 0
A-062 | CCTV | CCTV | PVC | 147-08-047 | 147-08-046 | 8 | HUMBER DR | 13/14 | 299 | 299 | [15 empty] | 0 |  | 3
A-063 | CCTV, JC | CCTV, JC | PVC | 147-08-048 | 147-08-047 | 8 | HUMBER DR | 13/14 | 69 | 69 | [15 empty] | 0 |  | 2
A-064 | S-LL (1) | S-LL (1) | PVC | 147-08-049 | 147-04-079 | 8 | TORBAY DR | 9/10/13/14 | 269 | 288 | 2026-04-06 | Downstream | 288 | 287.4 | 3 | 8.5' | 8" | 7.9' | 8" | PVC | NA | Ready to Line | B-3 |  |  | 0 |  | 3
A-069 | S-LTV (2) | S-LTV (2) | PVC | 147-08-054 | 147-08-053 | 8 | WALES CT | 13/14 | 269 | 269 | [15 empty] | 0 |  | 4
A-070 | CCTV, JC | CCTV, JC | PVC | 147-08-055 | 147-08-054 | 8 | WALES CT | 13/14 | 157 | 157 | [15 empty] | 0 |  | 3
A-071 | S-LTV(1) | S-LTV(1) | PVC | 147-08-056 | 147-08-055 | 8 | WALES CT | 13/14 | 125 | 125 | [15 empty] | 0 |  | 2
A-072 | CCTV, S-PR (1), IR (2) | CCTV, S-PR (1), IR (2) | PVC | 147-08-057 | 147-08-056 | 8 | WALES CT | 13/14 | 91 | 91 | [15 empty] | 0 |  | 2
A-075 | CCTV, JC, EX (1), S-PR (1), IR (2) | CCTV, JC, EX (1), S-PR (1), IR (2) | PVC | 147-08-060 | 147-08-059 | 8 | WALES CT | 13/14 | 183 | 183 | [15 empty] | 0 |  | 3
A-076 | CCTV; JC; EX (2) | CCTV; JC; EX (2) | PVC | 147-08-061 | 147-08-060 | 8 | WALES CT | 13/14 | 255 | 255 | [15 empty] | 0 |  | 2
A-077 | CCTV, JC | CCTV, JC | PVC | 147-08-062 | 147-08-061 | 8 | WALES CT | 13/14 | 292 | 292 | [15 empty] | 0 |  | 3
A-078 | S-LTV (1) | S-LTV (1) | PVC | 147-08-063 | 147-08-062 | 8 | WALES DR | 13/14 | 80 | 80 | [15 empty] | 0 |  | 3
A-083 | IR | CCTV; IR | PVC | 147-08-068 | 147-08-067 | 8 | WALES DR | 22/23 | 227 | 227 | [15 empty] | 0 |  | 1
A-086 | CCTV, JC | CCTV, JC | PVC | 147-08-071 | 147-08-070 | 8 | WALES DR | 13/14 | 145 | 145 | [15 empty] | 0 |  | 2
A-088 | S-PR (2), IR (4) | CCTV; S-PR (2), IR (4) | PVC | 147-08-073 | 147-08-071 | 8 | HOPEDALE DR | 13/14 | 270 | 270 | [15 empty] | 0 |  | 3
A-093 | CCTV, JC, S-PR(2), IR (4) | CCTV, JC, S-PR(2), IR (4) | PVC | 147-08-078 | 147-08-077 | 8 | HUMBER DR | 13/14 | 128 | 128 | [15 empty] | 0 |  | 2
A-097 | CCTV | CCTV | DIP | 147-08-082 | 147-08-074 | 8 | HOPEDALE DR | 13/14 | 215 | 215 | [15 empty] | 0 |  | 0
A-098 | CCTV, JC | CCTV, JC | PVC | 147-08-096 | 147-08-100 | 8 | HOLLIS HILL DR | 13/14 | 173 | 173 | [15 empty] | 0 |  | 1
A-100 | CIPP, S-PR(4), IR (8) | CIPP | VCP | 147-08-098 | 147-08-012 | 8 | FAULKNER DR | 13/14 | 325 | 325 | [15 empty] | 0 |  | 4
A-102 | CCTV | CCTV | PVC | 147-08-100 | 147-08-098 | 8 | HOLLIS HILL DR | 13/14 | 124 | 124 | [15 empty] | 0 |  | 0
A-103 | CCTV, JC | CCTV, JC | DIP | 147-08-101 | 147-08-102 | 8 | HOLLIS HILL DR | 13/14 | 212 | 212 | [15 empty] | 0 |  | 3
A-104 | CCTV | CCTV | PVC | 147-08-102 | 147-08-096 | 8 | HOLLIS HILL DR | 13/14 | 204 | 204 | [15 empty] | 0 |  | 3
A-106 | CIPP | CIPP | UNK | 148-09-029 | 148-09-030 | 8 | FAULKNER DR | 19/20 | 108 | 108 | [15 empty] | 0 |  | 4
A-108 | CCTV | CCTV | PVC | 147-12-043 | 147-12-064 | 8 | CARAWAY DR | 17/18 | 138 | 138 | [15 empty] | 0
A-110 | CCTV | CCTV | PVC | 147-12-045 | 147-12-063 | 8 | CARAWAY DR | 17/18 | 142 | 142 | [15 empty] | 0
A-111 | CCTV | CCTV | DIP | 147-12-046 | 147-08-040 | 8 | CARAWAY DR | 13/14/17/18 | 153 | 153 | [15 empty] | 0 |  | 0
A-123 | CCTV | CCTV | PVC | 147-12-063 | 147-12-046 | 8 | CARAWAY DR | 17/18 | 159 | 159 | [15 empty] | 0 |  | 1
A-124 | CCTV | CCTV | PVC | 147-12-064 | 147-12-044 | 8 | CARAWAY DR | 17/18 | 139 | 139 | [15 empty] | 0
A-126 | CIPP, S-PR (3), IR (6) | CIPP | VCP | 148-01-036 | 147-08-018 | 8 | TURLEY DR | 9/10/11/12/13/14 | 229 | 229 | [15 empty] | 0 |  | 3
A-127 | CIPP, EX, S-PR (1), IR (2) | CIPP | VCP | 148-01-037 | 148-01-036 | 8 | TURLEY DR | 11/12 | 114 | 114 | [15 empty] | 0 |  | 1
A-128 | JC, CIPP, S-PR(1), IR (2) | CIPP | VCP | 148-01-038 | 148-01-037 | 8 | TURLEY DR | 11/12 | 91 | 91 | [15 empty] | 0 |  | 1
A-129 | CIPP | CIPP | VCP | 148-01-039 | 147-04-053 | 8 | WILLOW LN | 9/10/11/12 | 196 | 199 | 2026-04-02 | Upstream | 199 | 198.9 | 4 | 5.6' | 8" | 5.9' | 8" | VCP | NA | Needs Attention | B-3 | MATERIAL SETTLED/BONDED TO PIPE 1-2' FROM USMH 148-01-039 / INFILTRATION 124.6' FROM DSMH 147-04-053 |  | 0 |  | 4
A-130 | CIPP | CIPP | VCP | 148-01-040 | 148-01-039 | 8 | WILLOW LN | 11/12 | 132 | 133 | 2026-04-02 | Upstream | 133 | 132.7 | 2 | 5.4' | 8" | 5.6' | 8" | VCP | NA | Ready to Line | B-3 |  |  | 0 |  | 2
A-131 | CIPP, S-PR(5), IR (10) | CIPP | VCP | 148-01-041 | 147-04-046 | 8 | WALLACE RD | 9/10/11/12 | 189 | 189 | [15 empty] | 0 |  | 5
A-132 | CCTV, S-PR (2), IR (4), S-LTV (3) | CCTV, S-PR (2), IR (4), S-LTV (3) | CIPP | 148-01-042 | 148-01-041 | 8 | WALLACE RD | 11/12 | 282 | 282 | [15 empty] | 0 |  | 3
A-133 | CIPP; S-PR(2), IR (4) | CIPP | VCP | 148-01-043 | 148-01-042 | 8 | TURLEY DR | 11/12 | 103 | 103 | [15 empty] | 0 |  | 2
A-134 | CIPP, S-PR (2), IR (4) | CIPP | VCP | 148-01-044 | 148-01-043 | 8 | TURLEY DR | 11/12 | 165 | 165 | [15 empty] | 0 |  | 2
A-135 | CIPP | CIPP | VCP | 148-01-045 | 148-01-044 | 8 | TURLEY DR | 11/12 | 227 | 227 | [15 empty] | 0 |  | 4
A-136 | CCTV, JC, S-PR(2), IR (4) | CCTV, JC, S-PR(2), IR (4) | CIPP | 148-01-046 | 147-04-044 | 8 | WALLACE RD | 9/10/11/12 | 373 | 375 | 2026-04-06 | Downstream | 375 | 374.3 | 5 | 10.5' | 8" | 8.2' | 8" | PVC | NA | PVC | B-3 |  |  | 0 |  | 2
A-137 | CCTV, JC | CCTV, JC | CIPP | 148-01-047 | 148-01-046 | 8 | WALLACE RD | 11/12 | 379 | 371 | 2026-04-06 | Upstream | 371 | 370.8 | 4 | 6' | 8" | 10.5' | 8" | CIPP | NA | Previously Lined | B-3 |  |  | 0 |  | 4
A-138 | CIPP, JC, S-PR(3), IR (6) | CIPP | VCP | 148-01-048 | 148-01-047 | 8 | WALLACE RD | 11/12 | 168 | 169 | 2026-04-03 | Downstream | 169 | 168.1 | 1 | 9.9' | 8" | 6' | 8" | CIPP | NA | Previously Lined | B-3 |  |  | 0 |  | 4
A-139 | CCTV, JC | CCTV, JC | CIPP | 148-01-072 | 148-01-048 | 8 | WALLACE RD | 11/12 | 67 | 72 | 2026-04-03 | Upstream | 72 | 71.1 | 2 | 4.5' | 8" | 9.9' | 8" | CIPP | NA | Previously Lined | B-3 |  |  | 0 |  | 2
A-140 | CCTV, JC, S-PR (1), IR (2) | CCTV, JC, S-PR (1), IR (2) | CIPP | 148-01-090 | 148-01-041 | 8 | WILLOW LN | 11/12 | 275 | 275 | [15 empty] | 0 |  | 3
A-141 | CCTV, IR(2) | CCTV, IR(2) | CIPP | 148-05-001 | 147-08-017 | 8 | LEOPOLE RD | 13/14/15/16 | 282 | 282 | [15 empty] | 0 |  | 2
A-142 | IR (3) | IR (3) | CIPP | 148-05-002 | 148-05-001 | 8 | LEOPOLE RD | 15/16 | 208 | 208 | [15 empty] | 0 |  | 3
A-143 | S-PR(1); IR(2); S-LTV (1) for service being relocated to MH; New MH as noted | CCTV; S-PR(1); IR(2); S-LTV (1) for service being relocated to MH; New MH as noted | CIPP | 148-05-003 | 148-05-002 | 8 | LEOPOLE RD | 15/16 | 312 | 312 | [15 empty] | 0 |  | 4
A-144 | CCTV | CCTV | CIPP | 148-05-004 | 147-08-017 | 8 | FAULKNER DR | 13/14/15/16 | 138 | 138 | [15 empty] | 0 |  | 1
A-147 | S-PR(1), IR (2) | CCTV; S-PR(1), IR (2) | CIPP | 148-05-007 | 148-05-004 | 8 | LEOPOLE RD | 15/16 | 169 | 169 | [15 empty] | 0 |  | 2
A-149 | EX(3); S-PR(3); IR(6) | CCTV; EX(3); S-PR(3); IR(6) | CIPP | 148-05-009 | 148-05-008 | 8 | LEOPOLE RD | 15/16 | 198 | 198 | [15 empty] | 0 |  | 3
A-150 | S-PR(1), IR (2) | CCTV; S-PR(1), IR (2) | CIPP | 148-05-010 | 148-05-009 | 8 | TURLEY DR | 15/16 | 89 | 89 | [15 empty] | 0 |  | 1
A-152 | CIPP, S-PR(7), IR (12) | CIPP | VCP | 148-05-012 | 148-05-011 | 8 | TURLEY DR | 15/16 | 332 | 332 | [15 empty] | 0 |  | 6
A-153 | CIPP; S-PR(1), IR (2) | CIPP | VCP | 148-05-013 | 147-08-018 | 8 | TURLEY DR | 13/14/15/16 | 61 | 61 | [15 empty] | 0 |  | 1
A-154 | CCTV | CCTV | PVC | 148-05-097 | 148-05-008 | 8 | TURLEY DR | 15/16 | 80 | 80 | [15 empty] | 0 |  | 1
A-157 | CCTV | CCTV | PVC | 147-04-104 | 147-04-105 | 8 | WALLACE Road | 9/10 | 173 | 173 | [15 empty] | 0 |  | 0
A-201 | CIPP; S-LL (1) | CIPP; S-LL (1) | CIP/CONC | 107-05-010 | 107-05-009 | 8 | ELISSA DR/DABBS AVE | 25/26 | 106 | 106 | [15 empty] | 0 |  | 1
A-202 | S-LL (5) | S-LL (5) | CIPP | 107-05-011 | 107-05-009 | 18 | ELISSA DR | 25/26 | 358 | 358 | [15 empty] | 0 |  | 5
A-203 | CIPP; S-LL(2) | CIPP; S-LL(2) | CONC | 107-05-012 | 107-05-010 | 8 | ELISSA DR | 25/26 | 361 | 361 | [15 empty] | 0 |  | 7
A-204 | S-LL (2) | S-LL (2) | CIPP | 107-05-013 | 107-05-011 | 18 | ELISSA DR | 25/26 | 143 | 143 | [15 empty] | 0 |  | 2
A-205 | S-LL(3) | S-LL(3) | CIPP | 107-05-014 | 107-05-013 | 15 | ELISSA DR | 25/26 | 285 | 285 | [15 empty] | 0 |  | 3
A-206 | CIPP; S-LL(7); IR(1) | CIPP; S-LL(7); IR(1) | CONC/CIP | 107-05-015 | 107-05-012 | 8 | PATRICIA DR | 25/26 | 339 | 339 | [15 empty] | 0 |  | 7
A-207 | CIPP; S-LL(2); EX | CIPP; S-LL(2); EX | CONC | 107-05-020 | 107-05-015 | 8 | PATRICIA DR | 25/26 | 245 | 245 | [15 empty] | 0 |  | 2
A-208 | CIPP; EX | CIPP; EX | CONC | 107-05-021 | 107-05-020 | 8 | KAREN DR | 25/26 | 110 | 110 | [15 empty] | 0 |  | 0
A-209 | CIPP; IR; S-LL (4) | CIPP; IR; S-LL (4) | CONC | 107-05-022 | 107-05-021 | 8 | KAREN DR | 25/26 | 182 | 182 | [15 empty] | 0 |  | 4
A-210 | CIPP; IR; S-LL(5) | CIPP; IR; S-LL(5) | CONC | 107-05-024 | 107-05-020 | 8 | PATRICIA DR | 25/26 | 393 | 393 | [15 empty] | 0 |  | 5
A-211 | CIPP; S-LL(3) | CIPP; S-LL(3) | CONC | 107-05-025 | 107-05-021 | 8 | PATRICIA DR | 25/26 | 325 | 325 | [15 empty] | 0 |  | 3
A-212 | CIPP; S-LL(2) | CIPP; S-LL(2) | VCP | 107-05-052 | 107-05-053 | 8 | PATRICIA DR | 25/26 | 152 | 152 | [15 empty] | 0 |  | 2
A-213 | CCTV; IR(2) | CCTV; IR(2) | CIPP | 107-05-054 | 107-05-014 | 8 | ELISSA DR | 25/26 | 113 | 113 | [15 empty] | 0 |  | 0
A-214 | CIPP; S-LL(4) | CIPP; S-LL(4) | CONC | 107-05-077 | 107-05-024 | 8 | PATRICIA DR | 25/26 | 268 | 268 | [15 empty] | 0 |  | 4
A-215 | CIPP; IR | CIPP; IR | VCP | 107-05-081 | 107-05-022 | 8 | KAREN DR | 25/26 | 201 | 201 | [15 empty] | 0 |  | 0
A-216 | CIPP; EX (2); S-LL(3) | CIPP; EX (2); S-LL(3) | VCP | 107-05-082 | 107-05-081 | 8 | KAREN DR | 25/26 | 164 | 164 | [15 empty] | 0 |  | 4
A-217 | CIPP; S-LL(4); | CIPP; S-LL(4); | CONC | 107-05-087 | 107-05-077 | 8 | PATRICIA DR | 25/26 | 191 | 191 | [15 empty] | 0 |  | 4
A-218 | CIPP; IR; S-LL(4) | CIPP; IR; S-LL(4) | VCP | 107-09-039 | 107-005-083 | 8 | FIVE OAKS DR | 25/26/27/28 | 239 | 239 | [15 empty] | 0 |  | 4
A-219 | CIPP; IR(1) | CIPP; IR(1) | VCP | 107-09-041 | 107-09-040 | 8 | MASSMAN DR | 27/28 | 61 | 61 | [15 empty] | 0 |  | 0
A-220 | S-LL(1) | S-LL(1) | DIP | 107-09-042 | 107-09-041 | 8 | MASSMAN DR | 27/28 | 141 | 141 | [15 empty] | 0 |  | 1
A-221 | CIPP; S-LL (1) | CIPP; S-LL (1) | VCP | 107-09-043 | 107-09-042 | 8 | MASSMAN DR | 27/28 | 136 | 136 | [15 empty] | 0 |  | 1
A-222 | S-LL(1) | S-LL(1) | DIP | 107-09-044 | 107-09-043 | 8 | MASSMAN DR | 27/28 | 128 | 128 | [15 empty] | 0 |  | 1
A-223 | CIPP; S-LL(2) | CIPP; S-LL(2) | VCP | 107-09-045 | 107-09-044 | 8 | MASSMAN DR | 27/28 | 166 | 166 | [15 empty] | 0 |  | 2
A-224 | CIPP; S-LL(1) | CIPP; S-LL(1) | VCP | 107-09-046 | 107-09-045 | 8 | MASSMAN DR | 27/28 | 75 | 75 | [15 empty] | 0 |  | 1
A-225 | CIPP; S-LL(1) | CIPP; S-LL(1) | VCP | 107-09-049 | 107-09-048 | 8 | MASSMAN DR | 27/28 | 57 | 57 | [15 empty] | 0 |  | 1
A-226 | CIPP | CIPP | CONC/CIP | 107-10-015 | 107-10-002 | 12 | GLASTONBURY BLVD | 29/30 | 60 | 60 | [15 empty] | 0 |  | 0
[10 empty] | 0 | [15 empty] | 0
[10 empty] | 0 | [15 empty] | 0
[10 empty] | 0 | [15 empty] | 0
[10 empty] | 0 | [15 empty] | 0
[10 empty] | 0 | [15 empty] | 0
[10 empty] | 0 | [15 empty] | 0
[10 empty] | 0 | [15 empty] | 0
[10 empty] | 0 | [15 empty] | 0
[10 empty] | 0 | [15 empty] | 0
[10 empty] | 0 | [15 empty] | 0